## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Boyermari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000359/2022-2023 | 2237/BD | 28/07/2022 | 27/08/2022 | M/S K.P.PAL. | 44.4 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (replacement) under Boyermari Abad W/S Scheme in Sandeshkhali-I Block District of North 24 Pgs. Tender No.- 1452(Sl. No.-04) of EE/EMD of 2022-23, (1) Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC |  |  | ORD/001975/2022-2023 | 3386/ EMD | 14/08/2022 | 14/08/2023 | M.S.C. ENTERPRISE | 10.81 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under Boyermari W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001901/2022-2023 | 3385 / EMD | 14/08/2022 | 13/09/2022 | PERFECT AIR CONDITIONER | 10.82 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Boyermari Abad water supply scheme, Sandeshkhali-I Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000669/2022-2023 | 2928/BD | 26/09/2022 | 25/12/2022 | S.S.ENTERPRISE. (BAMANGACHI) | 370.05 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Boyermari Abad W/S Scheme in Sandeshkhali-I Block District of North 24 Pgs. Tender No.- 08(Sl. No.-04) of EE/EMD of 2022-23 |  |  | ORD/001668/2022-2023 | 3385 /EMD | 14/08/2022 | 13/09/2022 | PERFECT AIR CONDITIONER | 10.82 | 0 | 0 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Boyermari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer |  | ORD/000259/2023-2024 | 785/HSD | 13/07/2023 | 23/07/2023 | MD.SALIM GAZI. | 0.87 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000246/2022-2023 | 931/BD | 22/03/2023 | 22/03/2023 | Resource Division | 9.92 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Boyermari Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000582/2024-2025 | 1179/HSD | 30/09/2024 | 10/10/2024 | M/S DATTA ENTERPRISE. | 0.89 | 0 | 0 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Acceptance cum work order for Emergent withdrawing, relaying and laying of different dia. UPVC/DI pipe line at Boyermari Abad water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E.Dte | Assistant Engineer |  | ORD/001405/2024-2025 | 512/BD | 17/02/2025 | 18/04/2025 | MUKHERJEE CONSTRUCTION (NADIA) | 17.75 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion (River side), protection works & other allied works in connection with Augmentation of Boyermari Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000512/2024-2025 | 3129/BD | 12/11/2024 | 09/08/2025 | S.S.ENTERPRISE. (BAMANGACHI) | 245.45 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Formal work order for Construction of 350 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Boyermari Abad water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000217/2023-2024 | 1732/BD | 08/06/2023 | 30/03/2025 | M/S DATTA ENTERPRISE. | 152.98 | 0 | 0 | 72
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | SM/10371 | Augmentation | Acceptance cum work order Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Boyermari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000890/2024-2025 | 3377/BD | 02/12/2024 | 31/01/2025 | M/S K.P.PAL. | 25.88 | 0 | 0 | 100
Total | [13 empty] | 900.65 | 0 | 0