## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000245/2022-2023 | 939/BD | 22/03/2023 | 22/03/2023 | Resource Division | 9.92 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Baunia Abad water supply scheme, Sandeshkhali-I Block within Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000659/2022-2023 | 2721/BD | 14/09/2022 | 13/12/2022 | KINGS & CO. | 452.15 | 393.02 | 86.92 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000015/2023-2024 | 1201/BD | 20/04/2023 | 20/05/2023 | M/S NIRMAN CONSTRUCTION. | 62.06 | 43.71 | 70.43 | 56
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connectin with Augmentation of Baunia Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001916/2023-2024 | 288/HSD | 06/03/2024 | 16/03/2024 | DEBAPRASAD MONDAL. | 0.84 | 0.84 | 100 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001361/2024-2025 | 350/BD | 31/01/2025 | 01/05/2025 | M/S DATTA ENTERPRISE. | 223.88 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000797/2024-2025 | 3303/BD | 27/11/2024 | 24/08/2025 | JOY GURU ENTERPRISE | 63.39 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for additional Construction of 2 nos. switch room cum chlorine room (5.40x3.60) for augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000012/2025-2026 | 1633/BD | 20/05/2025 | 19/07/2025 | JAGANNATH CONSTRUCTION. | 18.2 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Formal work order for construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Baunia Abad water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000141/2023-2024 | 1724/BD | 08/06/2023 | 31/03/2025 | DEBAPRASAD MONDAL. | 187.27 | 151.07 | 80.67 | 100
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Baunia Abad W/S Scheme District of North 24 Pgs. Tender No.- 08(Sl. No.-06) of EE/EMD of 2022-23 | Assistant Engineer | Junior Engineer | ORD/002673/2022-2023 | 3387EMD | 09/09/2022 | 01/04/2025 | GOENKA ENTERPRISE | 11.36 | 10.21 | 89.85 | 10
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (replacement) under Baunia Abad W/S Scheme District of North 24 Pgs. | Assistant Engineer | Junior Engineer | ORD/002675/2022-2023 | 3388EMD | 09/09/2022 | 01/04/2025 | POLYCON ENGINEERS | 11.36 | 10.55 | 92.87 | 10
11 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Additional work i.c.w. Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No- I (Replacement) under Bounia Abad W/S Scheme, Dist. 24 Pgs (N) | Assistant Engineer | Junior Engineer | ORD/000363/2024-2025 | 952/EMSD-I | 12/08/2024 | 22/08/2024 | GOENKA ENTERPRISE | 0.42 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Baunia Abad water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001454/2024-2025 | 335/HSD | 06/02/2025 | 16/02/2025 | M/S PROGATI ENTERPRISE. | 0.88 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Additional work icw Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug.work related to FHTC) at Pump House No.II (replacement) under Boania Abad W/S Scheme, District of 24 Pgs.(N). | Assistant Engineer | Junior Engineer | ORD/000420/2024-2025 | 957/EMSD-I | 12/08/2024 | 22/08/2024 | POLYCON ENGINEERS | 0.42 | 0.39 | 93.5 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Baunia Abad water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001462/2024-2025 | 339/HSD | 06/02/2025 | 16/02/2025 | M/S PROGATI ENTERPRISE. | 0.88 | 0 | 0 | 100
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at Madhya Baunia Jatindra Adarsha Jr. High School, Baunia 24 no Sabkhali para SSK, Baunia 25 no Booth SSK and Chotto Sehara Thakurmoni FP School within the command area of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001919/2024-2025 | 546/HSD | 10/03/2025 | 20/03/2025 | SARKAR ENTERPRISE | 0.96 | 0 | 0 | 100
Total | [13 empty] | 1043.99 | 609.79 | 58.41