## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000245/2022-2023 | 939/BD | 22/03/2023 | 22/03/2023 | Resource Division | 9.92 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000797/2024-2025 | 3303/BD | 27/11/2024 | 26/01/2025 | JOY GURU ENTERPRISE | 63.39 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Baunia Abad water supply scheme, Sandeshkhali-I Block within Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000659/2022-2023 | 2721/BD | 14/09/2022 | 13/12/2022 | KINGS & CO. | 452.15 | 393.02 | 86.92 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000015/2023-2024 | 1201/BD | 20/04/2023 | 20/05/2023 | M/S NIRMAN CONSTRUCTION. | 62.06 | 43.71 | 70.43 | 56
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connectin with Augmentation of Baunia Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001916/2023-2024 | 288/HSD | 06/03/2024 | 16/03/2024 | DEBAPRASAD MONDAL. | 0.84 | 0.84 | 100 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001361/2024-2025 | 350/BD | 31/01/2025 | 01/05/2025 | M/S DATTA ENTERPRISE. | 223.88 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for additional Construction of 2 nos. switch room cum chlorine room (5.40x3.60) for augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000012/2025-2026 | 1633/BD | 20/05/2025 | 19/07/2025 | JAGANNATH CONSTRUCTION. | 18.2 | 0 | 0 | 0
Total | [13 empty] | 830.44 | 437.57 | 52.69