## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000368/2022-2023 | 2244/BD | 28/06/2022 | 28/07/2022 | SHIBU BISWAS. | 54.44 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Formal work order for construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Baunia Abad water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000141/2023-2024 | 1724/BD | 08/06/2023 | 07/06/2024 | DEBAPRASAD MONDAL. | 187.27 | 29.14 | 15.56 | 75
3 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Baunia Abad W/S Scheme District of North 24 Pgs. Tender No.- 08(Sl. No.-06) of EE/EMD of 2022-23 |  |  | ORD/002673/2022-2023 | 3387EMD | 09/09/2022 | 09/10/2022 | GOENKA ENTERPRISE | 11.36 | 9.95 | 87.56 | 10
4 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (replacement) under Baunia Abad W/S Scheme District of North 24 Pgs. |  |  | ORD/002675/2022-2023 | 3388EMD | 09/09/2022 | 09/10/2022 | POLYCON ENGINEERS | 11.36 | 9.96 | 87.65 | 10
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000797/2024-2025 | 3303/BD | 27/11/2024 | 26/01/2025 | JOY GURU ENTERPRISE | 63.39 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Additional work i.c.w. Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No- I (Replacement) under Bounia Abad W/S Scheme, Dist. 24 Pgs (N) | Assistant Engineer | Junior Engineer | ORD/000363/2024-2025 | 952/EMSD-I | 12/08/2024 | 22/08/2024 | GOENKA ENTERPRISE | 0.42 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Additional work icw Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug.work related to FHTC) at Pump House No.II (replacement) under Boania Abad W/S Scheme, District of 24 Pgs.(N). | Assistant Engineer | Junior Engineer | ORD/000420/2024-2025 | 957/EMSD-I | 12/08/2024 | 22/08/2024 | POLYCON ENGINEERS | 0.42 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Baunia Abad water supply scheme, Sandeshkhali-I Block within Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000659/2022-2023 | 2721/BD | 14/09/2022 | 13/12/2022 | KINGS & CO. | 452.15 | 371.53 | 82.17 | 1
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000015/2023-2024 | 1201/BD | 20/04/2023 | 20/05/2023 | M/S NIRMAN CONSTRUCTION. | 62.06 | 0 | 0 | 56
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connectin with Augmentation of Baunia Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001916/2023-2024 | 288/HSD | 06/03/2024 | 16/03/2024 | DEBAPRASAD MONDAL. | 0.84 | 0 | 0 | 100
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. | SM/10374 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000245/2022-2023 | 939/BD | 22/03/2023 |  | Resource Division | 9.92 | 0 | 0 | 0
Total | [13 empty] | 853.62 | 420.57 | 49.27