## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Sindrani(ZI&II) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002939/2021-2022 | 594/BON | 22/12/2021 | 12/01/2022 | GHOSH CONSTRUCTION. | 2.52 | 2.34 | 92.64 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II(Z-I) under Sindrani W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 11) |  |  | ORD/002287/2022-2023 | 6148 /EMD | 14/08/2022 | 13/09/2022 | DIPALI CONSTRUCTION | 15 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Sindrani W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001898/2022-2023 | 6148 / EMD | 14/08/2022 | 13/09/2022 | DIPALI CONSTRUCTION | 12.81 | 9.06 | 70.76 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I Z-I under Sindrani W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001902/2022-2023 | 6147 / EMD | 14/08/2022 | 13/09/2022 | RAKA ENTERPRISE | 12.85 | 11.96 | 93.06 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Sindrani (Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | Assistant Engineer | Junior Engineer | ORD/000010/2022-2023 | 1210/BD | 21/04/2022 | 20/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 299.02 | 42.84 | 14.33 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Sindrani (Zone-I) water supply scheme (Head Works site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000828/2022-2023 | 3622/BD | 12/12/2022 | 27/12/2022 | NADIA TUBEWELLS | 15.06 | 12.32 | 81.82 | 0
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Supply, delivery and fitting fixing of change over switch, cable etc. at pump house no. I (Z-I), under Sindrani W/S Scheme in connection with FHTC. |  | Junior Engineer | ORD/001184/2023-2024 | 1773/EMSD-I | 10/08/2023 | 20/08/2023 | RAKA ENTERPRISE | 2.39 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 1364/BD | 13/05/2022 | 13/05/2022 | Resource Division | 33.31 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 1675/BD | 13/06/2022 | 13/06/2022 | Resource Division | 16.72 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 2374/BD | 12/08/2022 | 12/08/2022 | Resource Division | 60.89 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Health assessment of existing OHR of Sindrani (Zone-I) PWSS (135 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000012/2024-2025 | 685/Bon | 07/06/2024 | 22/06/2024 | RISHAN ENGINEERING CONSULTANCY | 3.12 | 3.12 | 100 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and tube well connection under Augmentation work at Sindrani W/S Scheme (Zone - I) Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000085/2024-2025 | 1766/BD | 01/07/2024 | 16/07/2024 | ONKAR ENTERPRISE. | 19.03 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Acceptance cum work order for Hire and labour charges for staging and scaffolding, bamboo baricading and removal of rubbish for dismantling of existing OHR at Head work Site of Sindrani Zone-I Water Supply Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001698/2024-2025 | 704/BD | 06/03/2025 | 04/07/2025 | ONKAR ENTERPRISE. | 7.1 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC | SM/10375 | Augmentation | Quotation for 10 KWp Solar power plant at P.H.No- I , Zone - I of Sindrani ground water based water supply scheme under EMSD-I ,PHE Dte. in Dist.- 24Pgs(N). |  |  | BILL/03025/2025-2026 |  | 07/01/2026 | 07/01/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.15 | 0 | 0 | 0
Total | [13 empty] | 499.95 | 81.63 | 16.33