## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Joygram Bazar Idgah to near Pintu Molla Garage for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000317/2022-2023 | 1238/HSD | 20/07/2022 | 10/08/2022 | JESMINE ENTERPRISE. | 4.76 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Restoration of RCC drain from N/H/O Sahidul Molla to near Julfikar Molla shop for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000325/2022-2023 | 1246/HSD | 20/07/2022 | 10/08/2022 | JESMINE ENTERPRISE. | 4.76 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Pintu Molla Garage to N/H/O Sahidul Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000319/2022-2023 | 1240/HSD | 20/07/2022 | 10/08/2022 | JESMINE ENTERPRISE. | 4.76 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Near Julfikar Molla shop to N/H/O Sariful Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000323/2022-2023 | 1244/HSD | 20/07/2022 | 10/08/2022 | JESMINE ENTERPRISE. | 3.39 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Laying of 150 mm dia. DI distribution main from near PH No-1 to N/H/O Prasanta Mondal, N/H/O Sudip Gayen to Chanchal Chatterjee & Sudip Gayen to Santanu Joardar for damage portion within Korakati w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000267/2022-2023 | 1189/HSD | 13/07/2022 | 28/07/2022 | R.K.MANDAL & CO. | 4.27 | 4.27 | 99.99 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Laying of 100mm dia. DI distribution main from N/H/O Chanchal Chatterjee to N/H/O Kritanta Mondal & Biswajit Baidya for damage portion within Korakati w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000269/2022-2023 | 1191/HSD | 13/07/2022 | 23/07/2022 | R.K.MANDAL & CO. | 2.17 | 2.17 | 100 | 1
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Laying of 200 mm dia. DI distribution main from PH No- 1 to PH No-2 & PH No- 2 to N/H/O Sudip Gayen for damage portion within Korakati w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000264/2022-2023 | 1186/HSD | 13/07/2022 | 28/07/2022 | R.K.MANDAL & CO. | 4.25 | 4.25 | 100 | 1
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator at (inconnection with Aug. work related to FHTC) Pump House No.II (Replacement) under Korakati W/S Scheme District of North 24 Pgs. |  |  | ORD/000024/2022-2023 | 3035/ EMD | 08/08/2022 | 07/09/2022 | SANKAR PRASAD DUTTA & CO, | 10.14 | 0 | 0 | 1
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2023-2024 | 1202/BD | 20/04/2023 | 20/05/2023 | TRISHA ENTERPRISE & CO. | 31.02 | 23.48 | 75.7 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000856/2023-2024 | 1042-HSD. | 31/08/2023 | 10/09/2023 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Korakati water supply scheme, Sandeshkhali-II Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000602/2022-2023 | 2675/BD | 08/09/2022 | 07/12/2022 | PATHIK PABAN NANDI | 274.1 | 265.59 | 96.89 | 1
12 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator at (inconnection with Aug. work related to FHTC) Pump House No.II (Replacement) under Korakati W/S Scheme District of North 24 Pgs. |  |  | ORD/001931/2022-2023 | 3035/EMD | 08/08/2022 | 08/03/2023 | SANKAR PROSAD DUTTA & CO. | 9.33 | 9.33 | 100 | 0
13 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Korakati W/S Scheme District of North 24 Pgs. Tender No.- 08 (Sl. No.-03) of EE/EMD of 2022-23 |  |  | ORD/002708/2022-2023 | 3384EMD | 09/09/2022 | 09/10/2022 | CHATTERJEE BROTHERS | 11.31 | 10.31 | 91.16 | 70
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000854/2023-2024 | 1041/HSD | 31/08/2023 | 10/09/2023 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0.9 | 100 | 100
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000855/2023-2024 | 1042/HSD | 31/08/2023 | 10/09/2023 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0.9 | 100 | 100
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Korakati water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001290/2023-2024 | 1412/HSD | 06/11/2023 | 13/11/2023 | ANKUSH CONSTRUCTION & CO. | 0.91 | 0.91 | 100 | 59
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 2576/BD | 31/08/2022 | 31/08/2022 | Resource Division | 6.15 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000257/2022-2023 | 918/BD | 22/03/2023 | 22/03/2023 | Resource Division | 10.9 | 0 | 0 | 0
19 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | illumination by supplying and installing of 15 Watt Solar Street Light at P.H No. I under Korakati W/S Scheme,Sandeshkhali-II Block, Dist. 24 pgs (N) under Eastern Mechanical Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2024-2025 | 1197/EMSD-I | 27/09/2024 | 27/10/2024 | P.K. ENTERPRISE | 1.5 | 0 | 0 | 0
20 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000844/2023-2024 | 2680/BD | 04/09/2023 | 04/10/2023 | ANKIT CONSTRUCTION | 66.88 | 66.57 | 99.53 | 82
21 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Supply delivery & fixing at site 4 Core, 50 Sq. Mm XLPE Al, Ar. Cable for shifting of service connection cable at Head Work site of Korakati W/S Scheme District of 24Pgs(N). | Assistant Engineer | Junior Engineer | ORD/003180/2023-2024 | 295/EMSD-I | 11/03/2024 | 21/03/2024 | TAKE ME INDIA | 0.55 | 0.55 | 100 | 100
22 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001295/2024-2025 | 865/BD | 19/03/2025 | 12/06/2026 | M/S K.B.ENTERPRISE. | 102.2 | 0 | 0 | 30
23 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Korakati water supply scheme, Sandeshkhali-II Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001253/2023-2024 | 4190/BD | 30/10/2023 | 06/02/2025 | M/S K.B.ENTERPRISE. | 140.14 | 102.12 | 72.87 | 85
24 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Korakati W/S Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-II) | Assistant Engineer | Junior Engineer | ORD/001605/2024-2025 | 469/HSD | 28/02/2025 | 10/03/2025 | PRASANTA MITRA. | 0.97 | 0 | 0 | 100
25 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Installation of CCTV Camera Connection at Pump house no 1 & 2 for Korakati w/s scheme, Sandeshkhali -II Block under Hasnabad Sub-Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/001339/2024-2025 | 186/HSD | 28/01/2025 | 07/02/2025 | M/S DATTA ENTERPRISE. | 0.58 | 0 | 0 | 100
26 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Supply and installation of 150 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces in connection with augmentation of Korakati water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000117/2025-2026 | 944/HSD | 29/05/2025 | 08/06/2025 | NEW LIFE CONSTRUCTION. | 0.83 | 0 | 0 | 100
27 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Korakati W/S Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001446/2024-2025 | 322/HSD | 04/02/2025 | 14/02/2025 | PRASANTA MITRA. | 0.96 | 0 | 0 | 100
28 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. | SM/10376 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Uttar Korakati SSK, Korakati Sishu Kalyan Vidyapith and Paschim Monipur Vijoy Das Smriti MSK within the command area of Korakati and Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000142/2025-2026 | 992/HSD | 04/06/2025 | 14/06/2025 | M/S RAJPATH CONSTRUCTION. | 0.72 | 0 | 0 | 100
Total | [13 empty] | 700.26 | 491.35 | 70.17