## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Fakiratakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000358/2022-2023 | 2236/BD | 28/07/2022 | 27/08/2022 | M/S K.P.PAL. | 44.41 | 15.19 | 34.21 | 1
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Fakirtakia W/S Scheme District of North 24 Pgs. NIET No.- 12 of EE/EMD of 2022-23 (Sl No.-02) |  |  | ORD/000092/2022-2023 | 5089/EMD | 04/11/2022 | 04/12/2022 | INDIA ENTERPRISE | 11.29 | 7.97 | 70.57 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near Chotto Ajgora in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000257/2023-2024 | 783/HSD | 13/07/2023 | 23/07/2023 | NEW LIFE CONSTRUCTION. | 0.94 | 0.94 | 100 | 29
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near Baro Ajgora in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000294/2023-2024 | 778/HSD | 13/07/2023 | 23/07/2023 | NEW LIFE CONSTRUCTION. | 0.89 | 0.89 | 100 | 29
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) for left out house holds under the command area of Fakirtakia water supply scheme in order to provide Har Ghar Jal Certification, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001722/2023-2024 | 372/BD | 06/02/2024 | 07/03/2024 | SARKAR ENTERPRISE & CO. | 47.73 | 0 | 0 | 75
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Fakirtakia water supply scheme, Sandeshkhali-I Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000596/2022-2023 | 2674/BD | 08/09/2022 | 07/12/2022 | PROJECT INDIA | 228.86 | 223.88 | 97.83 | 1
7 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I under Fakirtakia W/S Scheme District of North 24 Pgs. . NIT No.-12 of EE/EMD of 2022-23 (Sl. No.-01) | Assistant Engineer | Junior Engineer | ORD/000091/2022-2023 | 5088/EMD | 04/11/2022 | 04/12/2022 | ESENCE ENGINEERING CONCERN | 11.28 | 9.28 | 82.23 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near Bitpole in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000249/2023-2024 | 775/HSD | 13/07/2023 | 23/07/2023 | NEW LIFE CONSTRUCTION. | 0.94 | 0.94 | 100 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Formal work order for construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Fakirtakia water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000155/2023-2024 | 1722/BD | 08/06/2023 | 07/06/2024 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 153.55 | 41.47 | 27.01 | 72
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Acceptance cum work order for Supply, fitting & fixing of sluice valve with valve chember at HW & 2nd TW site in connection with augmentation of Fakitakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/001292/2023-2024 | 1414/HSD | 06/11/2023 | 13/11/2023 | BADAL GHOSH. | 0.79 | 0.4 | 50 | 100
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation for Fakirtakia water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001830/2023-2024 | 257/HSD | 06/03/2024 | 16/03/2024 | BADAL GHOSH. | 0.59 | 0 | 0 | 100
12 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near PH No- 1 in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000263/2023-2024 | 789/HSD | 13/07/2023 | 23/07/2023 | NEW LIFE CONSTRUCTION. | 0.98 | 0.98 | 100 | 31
13 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 2578/BD | 31/08/2022 |  | Resource Division | 6.15 | 0 | 0 | 0
14 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC | SM/10392 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000173/2022-2023 | 520/BD | 20/02/2023 |  | Resource Division | 14.66 | 0 | 0 | 0
Total | [13 empty] | 523.06 | 301.93 | 57.72