## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10502 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Sukhdaoni w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000153/2022-2023 | 1660/BD | 10/06/2022 | 08/09/2022 | SUPRITI ENTERPRISE. | 113.4 | 102.01 | 89.96 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10502 | Retrofitting | Acceptance cum work order for Hiring Diesel Luxury Car on Daily basis (for 6 months from 01.10.2022 to 31.03.2023) for the office use of the Executive Engineer, Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000805/2022-2023 | 2826/BD | 29/09/2022 | 28/03/2023 | MADHAB CHANDRA DAS | 0.89 | 1.56 | 175.09 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10502 | Retrofitting | Formal work order for Protection work for newly laid UPVC pipe line at different places of Sukhdoani Mouza in connection with retrofitting of Sukhdoani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000010/2023-2024 | 1165/BD | 13/04/2023 | 13/05/2023 | SUPRITI ENTERPRISE. | 68.84 | 68.78 | 99.91 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10502 | Retrofitting | Acceptance cum work order for Providing Functional tap connection at Sukhdoani (SPL) FP School, Dk. Sukhdoani FP School & Sukhdoani Dwarikanath FP School within the command area of Sukhdoani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000870/2023-2024 | 1056/HSD | 31/08/2023 | 07/09/2023 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 0.6 | 0.6 | 100 | 100
5 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10502 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at Head Work site (Ph No-1) within Sukhdoani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001309/2023-2024 | 4381/BD | 10/11/2023 | 08/02/2024 | ABDUL ALIM MONDAL. | 24.32 | 12.13 | 49.87 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10502 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Sukhdoani Mouza within Sukhdoani w/s scheme , Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000312/2024-2025 | 885/HSD | 07/08/2024 | 17/08/2024 | NEW LIFE CONSTRUCTION. | 0.96 | 0.48 | 49.95 | 0
Total | [13 empty] | 209.02 | 185.56 | 88.78