## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P | SM/10504 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Jeliakhali Purba Khanda W/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000088/2022-2023 | 1605/BD | 07/06/2022 | 05/09/2022 | SUBHASH BOSE. | 126.81 | 120.92 | 95.36 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P | SM/10504 | Retrofitting | Acceptance cum work order Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Jeliakhali Purba mouza within Jeliakhali Purbakhanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002835/2021-2022 | 533/HSD | 15/03/2022 | 30/03/2022 | PRITAM MUKHOPADHYAY. | 4.77 | 4.71 | 98.76 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P | SM/10504 | Retrofitting | Acceptance cum work order for Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Jeliakhali Purbakhanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000796/2024-2025 | 3314/BD | 27/11/2024 | 27/12/2024 | JOY GURU ENTERPRISE | 31.69 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P | SM/10504 | Retrofitting | Formal work order for Protection work in different places of Jeliakhali Mouza in connection with retrofitting of Jeliakhali Purba Khanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000091/2023-2024 | 1496/BD | 17/05/2023 | 16/06/2023 | SUBHASH BOSE. | 137.02 | 135.82 | 99.13 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P | SM/10504 | Retrofitting | Acceptance cum work order for Construction of boundary wall with brick masonry structure at Head Work site within Jeliakhali Purbakhanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/001311/2023-2024 | 4382/BD | 10/11/2023 | 08/02/2024 | MD.SALIM GAZI. | 28.33 | 26.22 | 92.53 | 68
Total | [13 empty] | 328.62 | 287.67 | 87.54