## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10505 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000093/2022-2023 | 1617/BD | 07/06/2022 | 05/09/2022 | RADIANT | 124.77 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10505 | Retrofitting | Formal work order for Protection work in different places of Jhupkhali Mouza in connection with retrofitting of Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000034/2023-2024 | 1324/BD | 28/04/2023 | 28/05/2023 | RADIANT | 112.53 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10505 | Retrofitting | Acceptance cum work order for Providing Functional tap connection at Dhulia Jhupkhali FP School, Dhulia Jhupkhali Jr. High School & Jhupkhali FP School within the command area of Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000866/2023-2024 | 1052/HSD | 31/08/2023 | 07/09/2023 | M/S RAJPATH CONSTRUCTION. | 0.53 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10505 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Jhupkhali mouza due to erosion of soil for heavy rain fall during monsoon season within Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000976/2023-2024 | 1064/HSD | 31/08/2023 | 10/09/2023 | JESMINE ENTERPRISE. | 0.98 | 0 | 0 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10505 | Retrofitting | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile in Laukhali and Jhupkhali w/s scheme, Sandeshkhali-I & II block respectively under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000879/2023-2024 | 2681/BD | 04/09/2023 | 04/10/2023 | SURYA ENTERPRISE. | 67.91 | 0 | 0 | 99
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10505 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at Head Work site (TW No-1) within Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001304/2023-2024 | 4377/BD | 10/11/2023 | 08/02/2024 | JESMINE ENTERPRISE. | 21.09 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10505 | Retrofitting | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site at PH No.-1 within Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001271/2024-2025 | 355/BD | 31/01/2025 | 17/03/2025 | B.S.ENTERPRISE. (BASIRHAT) | 27.86 | 0 | 0 | 0
Total | [13 empty] | 355.66 | 0 | 0