## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling near Baba Loknath Mandir, N/H/O Kalu Singh, Subrata Mondal at Rajbari Sundariakhali and other different places at Laukhali village in connection with retrofitting of Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000397/2022-2023 | 1336/HSD | 02/08/2022 | 12/08/2022 | NIKHIL SAMADDAR | 4.52 | 4.51 | 99.73 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Construction of anchor block for resting of 100/150 mm dia DI pipeline at different places within Laukhali Patharghata w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000238/2022-2023 | 1147/HSD | 12/07/2022 | 27/07/2022 | PRITAM MUKHOPADHYAY. | 4.06 | 3.97 | 97.84 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places at Laukhali Patharghata mouza in connection with retrofitting of Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000396/2022-2023 | 1335/HSD | 02/08/2022 | 12/08/2022 | NIKHIL SAMADDAR | 4.5 | 4.48 | 99.51 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Laukhali W/s scheme Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000085/2022-2023 | 1569/BD | 01/06/2022 | 30/08/2022 | M/S S.S.ENTERPRISE. (SOUTH) | 250.04 | 214.8 | 85.91 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order forProtection of newly laid UPVC pipe line by bamboo pilling at different places at Agarhati mouza in connection with retrofitting of Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000395/2022-2023 | 1334/HSD | 02/08/2022 | 12/08/2022 | K.T.ENGINEERING & CO. | 4.47 | 4.46 | 99.78 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Emergent casing of UPVC pipe line at different locations over Khal, channel, culverts, roads within Laukhali W/S Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002798/2021-2022 | 358/HSD | 23/02/2022 | 10/03/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.39 | 4.49 | 102.33 | 1
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Additional emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Patharghata Laukhali Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002803/2021-2022 | 363/HSD | 23/02/2022 | 10/03/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.76 | 4.76 | 99.92 | 1
8 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Agarhati Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002801/2021-2022 | 361/HSD | 23/02/2022 | 10/03/2022 | MD.SALIM GAZI. | 4.76 | 4.76 | 100 | 1
9 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Additional emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Agarhati Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002802/2021-2022 | 362/HSD | 23/02/2022 | 10/03/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.76 | 4.76 | 100 | 1
10 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Additional emergent resting of 200/250/300 mm dia DI pipeline by concrete block at different places within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002800/2021-2022 | 360/HSD | 23/02/2022 | 10/03/2022 | SARKAR ENTERPRISE | 4.31 | 4.26 | 98.78 | 1
11 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places of Laukhali Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000260/2022-2023 | 1169/HSD | 12/07/2022 | 27/07/2022 | M/S S.S.ENTERPRISE. (SOUTH) | 4.81 | 4.8 | 99.88 | 1
12 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Formal work order for Laying of DI rising main and DI/UPVC distribution pipe line and Construction of 700 cum capacity 20mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Laukhali water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001544/2021-2022 | 536/BD | 23/02/2022 | 23/02/2023 | M/S S.S.ENTERPRISE. (SOUTH) | 452.05 | 156.2 | 34.55 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Additional emergent resting of 100/150 mm dia DI pipeline by concrete block at different places within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002799/2021-2022 | 359/HSD | 23/02/2022 | 10/03/2022 | MD.SALIM GAZI. | 4.19 | 4.15 | 99.13 | 1
14 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Construction of boundary wall with brick masonry structure at Head Work site (Ph No-1) within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001319/2023-2024 | 4433/BD | 10/11/2023 | 08/02/2024 | MATRI ENTERPRISE | 16.97 | 0 | 0 | 100
15 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000157/2022-2023 | 156/BD | 18/01/2023 | 18/01/2023 | Resource Division | 35.12 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase | SM/10506 | Retrofitting | Acceptance cum work order for Construction of 100 cum/hr Iron Removal Plant with blower room & other allied works within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000192/2025-2026 | 2024/BD | 18/06/2025 | 15/11/2025 | FIDERE MARINE SERVICES PVT. LTD. | 38.3 | 0 | 0 | 0
Total | [13 empty] | 842.01 | 420.4 | 49.93