## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places of Boyermari Pandab para & Boyermari Gazipara in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000418/2022-2023 | 1350/HSD | 03/08/2022 | 13/08/2022 | ABDUL HAMID GAZI. | 4.38 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sankar Pradhan, Uttam Das at Pradhan para & N/H/O Asraf Molla at Gazi para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000387/2022-2023 | 1325/HSD | 02/08/2022 | 12/08/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.82 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Emergent resting of different dia UPVC/DI pipeline by UC bullah pile at different places in different mouza while laying of pipeline in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002857/2021-2022 | 573/HSD | 23/03/2022 | 07/04/2022 | S. GHOSH & ASSOCIATES PVT. LTD. | 2.83 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000163/2022-2023 | 1667/BD | 13/06/2022 | 11/09/2022 | S. GHOSH & ASSOCIATES PVT. LTD. | 266.33 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in Chunchura mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000473/2022-2023 | 1398/HSD | 08/08/2022 | 23/08/2022 | ABDUL ALIM MONDAL. | 4.8 | 0 | 0 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Nishith Patra, Tapas Patra at Boyermari Patra para & N/H/O Ramesh Mahato at Boyermari Mahato para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000388/2022-2023 | 1326/HSD | 02/08/2022 | 12/08/2022 | SARKAR ENTERPRISE | 4.81 | 0 | 0 | 1
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at N/H/O Sukumar Mahato to N/H/O Mansaram Mahato at 6 no. Boyermari in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000389/2022-2023 | 1327/HSD | 02/08/2022 | 12/08/2022 | M/S K.B.ENTERPRISE. | 4.52 | 0 | 0 | 1
8 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection work for newly laid different dia. UPVC/DI distribution pipeline at different places in Bayermari Mouza of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000487/2022-2023 | 2368/BD | 10/08/2022 | 09/09/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 60.68 | 0 | 0 | 1
9 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places within Boyermari mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000479/2022-2023 | 1404/HSD | 08/08/2022 | 23/08/2022 | M/S RAJPATH CONSTRUCTION. | 4.78 | 0 | 0 | 1
10 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sankar Pradhan, Uttam Das at Pradhan para & N/H/O Asraf Molla at Gazi para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000620/2022-2023 | 1325/HSD | 02/08/2022 | 12/08/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.82 | 0 | 0 | 1
11 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sibu Sardar at Boyermari Sardar para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000384/2022-2023 | 1322/HSD | 02/08/2022 | 12/08/2022 | M/S ANUBHAB CONSTRUCTION. | 4.42 | 0 | 0 | 1
12 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sibu Gayen at Boyermari Das para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000385/2022-2023 | 1323/HSD | 02/08/2022 | 12/08/2022 | M/S ANUBHAB CONSTRUCTION. | 4.5 | 0 | 0 | 1
13 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Shibcharan Mahato, Chottu Mahato, Arabinda Mahato, Gopal Mahato & Chitta Mahato at Boyermari Mahato para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000386/2022-2023 | 1324/HSD | 02/08/2022 | 12/08/2022 | KABASI ENTERPRISE. | 4.72 | 0 | 0 | 1
14 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at N/H/O Nirmal Sardar, Rohit Sardar, Naren Mali, Basudeb Mali at Boyermari Mali para & N/H/O Bablu Singh at Boyermari Choto Singh para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000390/2022-2023 | 1328/HSD | 02/08/2022 | 12/08/2022 | M/S LALTI ENTERPRISE | 3.63 | 0 | 0 | 1
15 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Emergent resting of 250/200 mm dia DI pipeline by concrete block over existing concrete wall beside Basanti Highway at different places for Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002847/2021-2022 | 563/HSD | 22/03/2022 | 06/04/2022 | MONDAL & CO. (BASIRHAT). | 4.41 | 0 | 0 | 1
16 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Additional emergent resting of 150/100 mm dia DI pipeline by concrete block over existing concrete wall beside Basanti Highway at different places for Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002848/2021-2022 | 564/HSD | 22/03/2022 | 06/04/2022 | ANKUSH CONSTRUCTION & CO. | 4.41 | 0 | 0 | 1
17 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Emergent casing of UPVC pipe line at different locations over Khal, channel, culverts, roads within Chunchura W/S Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002849/2021-2022 | 565/HSD | 22/03/2022 | 06/04/2022 | MONDAL & CO. (BASIRHAT). | 4.38 | 0 | 0 | 1
18 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Emergent resting of 100/150/200 mm dia DI pipeline by concrete block at different places from Kalupara more to N/H/O Sukumar Mahato within Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002850/2021-2022 | 566/HSD | 22/03/2022 | 06/04/2022 | ANKUSH CONSTRUCTION & CO. | 4.32 | 0 | 0 | 1
19 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Emergent resting of 100/150/200 mm dia DI pipeline by concrete block at different places from N/H/O Sukumar Mahato to Dheknimari High School within Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002851/2021-2022 | 567/HSD | 22/03/2022 | 06/04/2022 | MONDAL & CO. (BASIRHAT). | 4.32 | 0 | 0 | 1
20 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places within Boyermari mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002795/2021-2022 | 355/HSD | 23/02/2022 | 10/03/2022 | ABDUL ALIM MONDAL. | 4.78 | 0 | 0 | 1
21 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with retrofitting of Chunchura mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002796/2021-2022 | 356/hsd | 23/02/2022 | 10/03/2022 | M/S RAJPATH CONSTRUCTION. | 4.8 | 0 | 0 | 1
22 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Additional emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with retrofitting of Chunchura, Boyermari, Sankardaha Abad, Khas Sankardaha mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002797/2021-2022 | 357/HSD | 23/02/2022 | 10/03/2022 | M/S RAJPATH CONSTRUCTION. | 4.8 | 0 | 0 | 1
23 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Formal work order for Protection work in different places of Chunchura, Boyermari, Sankardaha & Sankardaha Abad Mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000118/2023-2024 | 1696/BD | 08/06/2023 | 08/07/2023 | AMAL DUTTA ROY | 140.16 | 0 | 0 | 81
24 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Laltu Sardar at Boyermari Sardar para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000419/2022-2023 | 1351/HSD | 03/08/2022 | 13/08/2022 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 4.42 | 0 | 0 | 1
25 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC/DI distribution pipeline by UC bullah pile at different places within Chunchura Mouza in Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000543/2022-2023 | 1811/ BD | 27/06/2022 | 27/07/2022 | MONDAL & CO. (BASIRHAT). | 76.73 | 0 | 0 | 1
26 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10509 | Retrofitting | Formal Work order for Laying of DI rising main and DI/UPVC distribution pipe line and Construction of 900 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chunchura & Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division,PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/003031/2021-2022 | 767/Bd | 16/03/2022 | 28/03/2022 | S. GHOSH & ASSOCIATES PVT. LTD. | 563.09 | 0 | 0 | 100
Total | [13 empty] | 1200.68 | 0 | 0