## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | SM/10514 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Janapul W/S Scheme and Bergum W/S Scheme with Pump House No-I, II And III under Gaighata W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001169/2023-2024 | 4797/EMD | 09/08/2023 | 01/03/2025 | MAHADEV ENTERPRISE | 74.15 | 0 | 0 | 57
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | SM/10514 | Augmentation | Construction of Service Road (20 Mtr. Length & 2 Mtr. Width) for Pump House No:3 of Bergum Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  | Junior Engineer | ORD/000358/2024-2025 | 702/HAB | 30/07/2024 | 14/08/2024 | ANJALI CONSTRUCTION. | 1.11 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | SM/10514 | Augmentation | Acceptance cum work order for Construction of the Boundary wall in Pump House No. 3 of Bergum Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000701/2024-2025 | 3159/BD | 14/11/2024 | 29/12/2024 | AREOCON. | 8.62 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | SM/10514 | Augmentation | Special repair and renovation of boundary wall and other allied Works for Pump House No - 1 of Bergum WS scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000597/2024-2025 | 913/HAB | 30/10/2024 | 29/11/2024 | AREOCON. | 1.91 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | SM/10514 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Bergum Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000560/2022-2023 | 2534/BD | 29/08/2022 | 27/11/2022 | UMWELT ENGINEER PVT.LTD. | 654.34 | 638.03 | 97.51 | 1
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | SM/10514 | Augmentation | Repairing & renovation of Pump House No. ? 1 & 2 of Bergum W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002980/2021-2022 | 502/HAB | 03/12/2021 | 02/01/2022 | AREOCON. | 2.07 | 2.06 | 99.55 | 1
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | SM/10514 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 of Bergum water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001535/2023-2024 | 06/BD | 02/01/2024 | 01/02/2024 | M/S B.K.ENTERPRISE. | 19.45 | 8.79 | 45.2 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | SM/10514 | Augmentation | Construction of Service Road (10 Mtr. Length & 2 Mtr. Width) for Pump House No:1 of Bergum Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001885/2023-2024 | 132/HAB | 05/02/2024 | 20/02/2024 | DEBASISH SARKAR. | 0.75 | 0 | 0 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | SM/10514 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 3109/BD | 18/10/2022 |  | Resource Division | 17.8 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC | SM/10514 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000127/2022-2023 | 3789/BD | 22/12/2022 |  | Resource Division | 26.74 | 0 | 0 | 0
Total | [13 empty] | 806.94 | 648.88 | 80.41