## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Repairing & renovation of Pump House No. - 1 & 2 of Gaighata W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002978/2021-2022 | 494/HAB | 02/12/2021 | 01/01/2022 | M/S SANKAR ENTERPRISE. | 2.95 | 2.9 | 98.2 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Repairing & renovation of Pump House No. ¿ 3 of Gaighata W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002982/2021-2022 | 511/HAB | 10/12/2021 | 09/01/2022 | M/S SANKAR ENTERPRISE. | 1.47 | 1.45 | 98.58 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2022-2023 | 3796/BD | 22/12/2022 | 22/12/2022 | Resource Division | 177.61 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 of Gaighata water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000047/2023-2024 | 1408/BD | 08/05/2023 | 07/06/2023 | NADIA TUBEWELLS | 28.98 | 25.15 | 86.78 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 3106/BD | 18/10/2022 | 18/10/2022 | Resource Division | 14.06 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 1555/BD | 23/05/2023 | 23/05/2023 | Resource Division | 7.44 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Janapul W/S Scheme and Bergum W/S Scheme with Pump House No-I, II And III under Gaighata W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001169/2023-2024 | 4797/EMD | 09/08/2023 | 01/03/2025 | MAHADEV ENTERPRISE | 74.15 | 16.05 | 21.65 | 57
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Special repair and renovation of pump house and other Allied Works for Pump House No - 1 of Gaighata WS scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000607/2024-2025 | 921/HAB | 30/10/2024 | 19/11/2024 | DEBASISH SARKAR. | 2.65 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Construction of Service Road 45 Mtr. Length X 2 Mtr. Width for Pump House No 1 of Gaighata Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/000604/2024-2025 | 917/HAB | 30/10/2024 | 09/11/2024 | M/S DAS & CO. | 2.75 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Construction of Service Road 17 Mtr. Length X 2 Mtr. Width for Pump House No 2 of Gaighata Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/000605/2024-2025 | 919/HAB | 30/10/2024 | 09/11/2024 | DEBANJAN GHOSH. | 1.04 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 3 for Augmentation of Gaighata water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000903/2023-2024 | 2778/BD | 11/09/2023 | 11/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 14.47 | 11.64 | 80.39 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of at Gaighata Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000559/2022-2023 | 2533/BD | 29/08/2022 | 09/02/2026 | SUPRITI ENTERPRISE. | 482.07 | 404.3 | 83.87 | 90
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Acceptance cum work order for Construction of Boundary Wall (110 m Length) for Pump House No - 1 of Gaighata water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000339/2024-2025 | 2283/BD | 13/08/2024 | 20/01/2025 | PUSPA CONSTRUCTION. | 16.34 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Improvement of Iron Elimination Plant including repairing of drain and other allied works of Gaighata W/S Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  | Junior Engineer | ORD/000340/2024-2025 | 692/HAB | 25/07/2024 | 24/08/2024 | M/S LATIKA CONSTRUCTION. | 4.07 | 4.06 | 99.77 | 100
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC | SM/10519 | Augmentation | Acceptance cum work order for Construction of Boundary Wall (70 m Length) for Pump House No - 2 of Gaighata water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000341/2024-2025 | 2285/BD | 13/08/2024 | 02/09/2024 | VAI ENTERPRISE. | 11.03 | 0 | 0 | 100
Total | [13 empty] | 841.06 | 465.54 | 55.35