## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | Augmentation | Repairing & renovation of Pump House No. ? 1 & 2 of Janaphul W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002981/2021-2022 | 503/HAB | 03/12/2021 | 02/01/2022 | AREOCON. | 1.3 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000126/2022-2023 | 3797/BD | 22/12/2022 | 22/12/2022 | Resource Division | 6.17 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 2 for Augmentation of Janaphul water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000911/2023-2024 | 2777/BD | 11/09/2023 | 11/10/2023 | M/S K.P.PAL. | 14.5 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2022-2023 | 3106/BD | 18/10/2022 | 18/10/2022 | Resource Division | 8.11 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 1556/BD | 23/05/2023 | 23/05/2023 | Resource Division | 0.92 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Janapul W/S Scheme and Bergum W/S Scheme with Pump House No-I, II And III under Gaighata W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001169/2023-2024 | 4797/EMD | 09/08/2023 | 01/03/2025 | MAHADEV ENTERPRISE | 74.15 | 0 | 0 | 57
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | Augmentation | Acceptance cum work order for construction of the Boundary wall in Pump House No. 2 of Janaphul Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000162/2024-2025 | 1799/BD | 01/07/2024 | 15/08/2024 | AREOCON. | 5.19 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | Augmentation | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of at Janaphul Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000546/2022-2023 | 2461/BD | 23/08/2022 | 21/11/2022 | UTPAL CONSTRUCTION & CO. | 230.82 | 0 | 0 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 2 of Janaphul water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000043/2023-2024 | 1407/BD | 08/05/2023 | 07/06/2023 | M/S K.P.PAL. | 14.5 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | Augmentation | Improvement of Iron Elimination Plant at Janaphul W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001424/2023-2024 | 692/HAB | 02/11/2023 | 02/12/2023 | GHOSH CONSTRUCTION | 4.51 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate | SM/10529 | Augmentation | Special repair & renovation of boundary wall and other allied Works for Pump House No - 1 of Janaphul W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001876/2023-2024 | 131/HAB | 05/02/2024 | 25/02/2024 | DEBANJAN GHOSH. | 0.77 | 0 | 0 | 100
Total | [13 empty] | 360.93 | 0 | 0