## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000133/2022-2023 | 3799/BD | 22/12/2022 | 22/12/2022 | Resource Division | 90.58 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 3107/BD | 18/10/2022 | 18/10/2022 | Resource Division | 9.23 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) and III(New) (Zone-II) under Durgapur-Baylani W/S Scheme with P/H-I, II and III(any 2 nos) under Kankpul W/S Scheme in District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer | ORD/001971/2022-2023 | 1285/EMD | 28/03/2023 | 27/04/2023 | BENGAL CONSTRUCTION | 60.96 | 0 | 0 | 40
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Continuation work order Hiring of 1 no. of Diesel Luxury Car (Euro - IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, For supervision of J.J.M. related work, executed within the entire Jurisdiction of Habra Sub-Division, under Barasat Division P.H.E. Dte.(For the period from: 01.03.2024 to 31.08.24) | Assistant Engineer | Junior Engineer | ORD/001795/2023-2024 | 211/HAB | 28/02/2024 | 28/08/2024 | M/S SUKANTA ENTERPRISE. | 0.87 | 1.97 | 225.63 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Acceptance cum work order for construction of Service Road(15 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of Kankpul Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/001896/2023-2024 | 169/HAB | 19/02/2024 | 05/03/2024 | M/S LATIKA CONSTRUCTION. | 0.92 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Special repair & renovation of pump house and other Allied Works for Pump House No - 2 of Kankpul W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000897/2024-2025 | 930/HAB | 05/11/2024 | 25/11/2024 | VAI ENTERPRISE. | 2.6 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Acceptance cum work order for Construction of Boundary Wall (75 m Length) for Pump House No - 3 of Kankpul water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer |  | ORD/000405/2024-2025 | 2581/BD | 05/09/2024 | 20/10/2024 | NEW MA TARA ENTERPRISE. | 11.91 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Construction of Service Road (35 Mtr. Length X 2 Mtr. Width) for Pump House No:3 of kankpul Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/000343/2024-2025 | 694/HAB | 25/07/2024 | 04/08/2024 | DEBASISH SARKAR. | 2.14 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Kankpul Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000562/2022-2023 | 2678/BD | 08/09/2022 | 07/12/2022 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 328.95 | 288.55 | 87.72 | 1
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Acceptance cum work order for Hiring Petrol Luxury Car on Daily basis (from20.08.2024 to 28.02.2025) for the office use of the Assistant Engineer(HQ), Barasat Division, PHE Dte | Assistant Engineer |  | ORD/000406/2024-2025 | 2341/BD | 16/08/2024 | 25/02/2025 | M/S B.K.ENTERPRISE. | 0.92 | 1.97 | 215.08 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Acceptance cum work order for Hiring Petrol Luxury Car on Daily basis for the office use of the Assistant Engineer(HQ), Barasat Division, PHE Dte. Period from 01.03.2025 to 31.08.2025. | Assistant Engineer |  | ORD/002467/2024-2025 | 643/BD | 28/02/2025 | 31/08/2025 | M/S B.K.ENTERPRISE. | 0.87 | 0.75 | 85.32 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate | SM/10530 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Kankpul water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000913/2023-2024 | 2775/BD | 11/09/2023 | 16/04/2025 | B.M.ENGINEERING. & CONSTRUCTION. | 28.92 | 0 | 0 | 100
Total | [13 empty] | 538.87 | 293.24 | 54.42