## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Repairing & renovation of Pump House No. - 1, 2 & 3 of Maslandapur W/S scheme (Zone - I) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002976/2021-2022 | 489/HAB | 30/11/2021 | 30/12/2021 | ANJALI CONSTRUCTION. | 2.77 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2022-2023 | 3794/BD | 22/12/2022 | 22/12/2022 | Resource Division | 21.91 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 2 & 3 for Augmentation of Maslandapur (Zone - I) water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000954/2023-2024 | 2773/BD | 11/09/2023 | 10/11/2023 | NADIA TUBEWELLS | 28.96 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.03.23 to 31.08.23 = 184 days. | Assistant Engineer |  | ORD/001146/2022-2023 | 0255/HSD | 28/02/2023 | 31/08/2023 | SUSMITA MANDAL. | 2.74 | 0 | 0 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Acceptance cum work order for Hiring of one no. DIESEL MOTOR CAB (BS-VI) on daily basis for smooth implementation of JJM work under office of the Assistant Engineer, HASNABAD SUB-DIVISION, PHE DTE. Period from 01.02.23 to 31.07.23. | Assistant Engineer | Junior Engineer | ORD/001349/2022-2023 | 137/HSD | 31/01/2023 | 31/07/2023 | SARKAR ENTERPRISE | 0.86 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Continuation order for Hiring of one no. Disel Motor Cab (BS-IV) on daily hire basis for use of the Assistant Engineer, Hasnabad Sub-Division, PHE Dte. Period from 01.10.2022 to 30.09.2023. | Assistant Engineer |  | ORD/001479/2022-2023 | 1656/HSD | 28/09/2022 | 28/09/2023 | SUSMITA MANDAL. | 1.72 | 0 | 0 | 50
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Maslandapur Water Supply Scheme (Zone - I) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000618/2022-2023 | 2720/BD | 14/09/2022 | 13/12/2022 | UMWELT ENGINEER PVT.LTD. | 512.52 | 0 | 0 | 1
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 1557/BD | 23/05/2023 | 23/05/2023 | Resource Division | 3.08 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II & III (Zone-I) under Maslandapur W/S Scheme and Pump House No-I an II uuder Kamarpur-Tazpur W/S Scheme (Rep.) District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.- 26) | Assistant Engineer | Junior Engineer | ORD/001976/2022-2023 | 1320/EMD | 29/03/2023 | 28/04/2023 | M/S DILIP MITRA | 53 | 0 | 0 | 80
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Acceptance cum work order for construction of the Boundary wall in Pump House No 2 & Pump House No. 3 of Maslandapur- I Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000166/2024-2025 | 1801/BD | 01/07/2024 | 15/08/2024 | ANJALI CONSTRUCTION. | 6.11 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Acceptance cum work order for construction of the Service Road (88.00 Mtr. Length & 3.00 Mtr. Wide while 1.00 Mtr. wide road already existing) in Head Work Site of Maslandapur- I Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000167/2024-2025 | 2209/BD | 06/08/2024 | 21/08/2024 | PUSPA CONSTRUCTION. | 5.6 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Head Work Site of Maslandapur water supply scheme (Zone - I) within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000046/2023-2024 | 1409/BD | 08/05/2023 | 07/06/2023 | NADIA TUBEWELLS | 14.49 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Improvement of Iron Elimination Plant at Maslandapur W/S Scheme (Zone - I) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001430/2023-2024 | 693/HAB | 02/11/2023 | 02/12/2023 | ANJALI CONSTRUCTION. | 4.78 | 0 | 0 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate | SM/10531 | Augmentation | Enhancement of GST for the work providing FHTC for Augmentation of Maslandapur (Zone-I) W/S Scheme |  |  | BILL/00274/2024-2025 | BP-2024-25-778 | 10/07/2024 | 10/07/2024 | UMWELT ENGINEER PVT.LTD. | 25.55 | 0 | 0 | 0
Total | [13 empty] | 684.1 | 0 | 0