## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Repairing & renovation of Pump House No. - 1 & 2 of Maslandapur W/S scheme (Zone - II) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002977/2021-2022 | 490/HAB | 30/11/2021 | 30/12/2021 | ANJALI CONSTRUCTION. | 2.18 | 2.17 | 99.72 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000124/2022-2023 | 3790/BD | 22/12/2022 | 22/12/2022 | Resource Division | 34.22 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 2515/BD | 25/08/2022 | 25/08/2022 | Resource Division | 22.72 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 1558/BD | 23/05/2023 | 23/05/2023 | Resource Division | 1.85 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II & III (Zone-II) under Maslandapur W/S Scheme (Rep.) District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.- 27) | Assistant Engineer | Junior Engineer | ORD/001977/2022-2023 | 1321/EMD | 29/03/2023 | 28/04/2023 | A.K. ENTERPRISE | 31.79 | 26.94 | 84.74 | 80
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | construction of the Service Road 35.00 Mtr. Length and 3.00 Mtr. Wide while 1.00 Mtr. wide road already existing in Head Work Site of Maslandapur- II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/000603/2024-2025 | 916/HAB | 30/10/2024 | 09/11/2024 | M/S GUHA CONSTRUCTION. | 2.26 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Acceptance cum work order for Construction of the Boundary wall in Pump House No. 2 of Maslandapur- II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000355/2024-2025 | 2410/BD | 22/08/2024 | 26/09/2024 | M/S MITRA CONSTRUCTION | 5.71 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Head Work Site of Maslandapur water supply scheme (Zone - II) within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000044/2023-2024 | 1406/BD | 08/05/2023 | 07/06/2023 | ARUN TRADERS | 14.49 | 13.43 | 92.69 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Improvement of Iron Elimination Plant at Maslandapur Zone II WS Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001406/2023-2024 | 671/HAB | 30/10/2023 | 29/11/2023 | S.G. ENTERPRISE | 4.47 | 4.42 | 98.78 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 2 of Maslandapur(Zone - II) water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001533/2023-2024 | 07/BD | 02/01/2024 | 01/02/2024 | M/S B.K.ENTERPRISE. | 19.45 | 16.71 | 85.91 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Construction of Service Road (10 Mtr. Length & 2 Mtr. Wide while 1.00 Mtr existing Road ) for Pump House No:2 of Maslandapur II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001886/2023-2024 | 134/HAB | 05/02/2024 | 20/02/2024 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 0.75 | 0.73 | 98.24 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Maslandapur Water Supply Scheme (Zone - II) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000534/2022-2023 | 2448/BD | 23/08/2022 | 08/02/2025 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 526.45 | 381.78 | 72.52 | 1
Total | [13 empty] | 666.32 | 446.18 | 66.96