## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Repairing & renovation of Pump House No. - 1 & 2 of Maslandapur W/S scheme (Zone - II) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002977/2021-2022 | 490/HAB | 30/11/2021 | 30/12/2021 | ANJALI CONSTRUCTION. | 2.18 | 2.17 | 99.72 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Maslandapur Water Supply Scheme (Zone - II) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000534/2022-2023 | 2448/BD | 23/08/2022 | 09/05/2025 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 526.45 | 381.78 | 72.52 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000124/2022-2023 | 3790/BD | 22/12/2022 | 22/12/2022 | Resource Division | 34.22 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 2515/BD | 25/08/2022 | 25/08/2022 | Resource Division | 22.72 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II & III (Zone-II) under Maslandapur W/S Scheme (Rep.) District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.- 27) | Assistant Engineer | Junior Engineer | ORD/001977/2022-2023 | 1321/EMD | 29/03/2023 | 28/04/2023 | A.K. ENTERPRISE | 31.79 | 26.94 | 84.74 | 80
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Head Work Site of Maslandapur water supply scheme (Zone - II) within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000044/2023-2024 | 1406/BD | 08/05/2023 | 07/06/2023 | ARUN TRADERS | 14.49 | 13.43 | 92.69 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Improvement of Iron Elimination Plant at Maslandapur Zone II WS Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001406/2023-2024 | 671/HAB | 30/10/2023 | 29/11/2023 | S.G. ENTERPRISE | 4.47 | 4.42 | 98.78 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 1558/BD | 23/05/2023 | 23/05/2023 | Resource Division | 1.85 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | construction of the Service Road 35.00 Mtr. Length and 3.00 Mtr. Wide while 1.00 Mtr. wide road already existing in Head Work Site of Maslandapur- II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/000603/2024-2025 | 916/HAB | 30/10/2024 | 09/11/2024 | M/S GUHA CONSTRUCTION. | 2.26 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Acceptance cum work order for Construction of the Boundary wall in Pump House No. 2 of Maslandapur- II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000355/2024-2025 | 2410/BD | 22/08/2024 | 26/09/2024 | M/S MITRA CONSTRUCTION | 5.71 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 2 of Maslandapur(Zone - II) water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001533/2023-2024 | 07/BD | 02/01/2024 | 01/02/2024 | M/S B.K.ENTERPRISE. | 19.45 | 16.71 | 85.91 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Construction of Service Road (10 Mtr. Length & 2 Mtr. Wide while 1.00 Mtr existing Road ) for Pump House No:2 of Maslandapur II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001886/2023-2024 | 134/HAB | 05/02/2024 | 20/02/2024 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 0.75 | 0.73 | 98.24 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Construction of Service Road (10 Mtr. Length & 2 Mtr. Width) for Pump House No:3 of Maslandapur II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  | Junior Engineer | ORD/001887/2023-2024 | 135/HAB | 05/02/2024 | 20/02/2024 | JOY ENTERPRISE | 0.6 | 0.6 | 99.52 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Acceptance cum work order for Construction of the Boundary wall in Pump House No. 3 of Maslandapur- II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2024-2025 | 2409/BD | 22/08/2024 | 06/10/2024 | JOY ENTERPRISE | 6.1 | 6.04 | 99.02 | 100
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Acceptance cum work order for Construction of boundary wall for raising height, drain and repairing of existing boundary wall for the Head Work site of Maslandapur II Piped water supply scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000702/2024-2025 | 3160/BD | 14/11/2024 | 24/12/2024 | S.G. ENTERPRISE | 5.12 | 0 | 0 | 100
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation | Repair and renovation of High Lift Pump House, Clorine Room and CWR in the Head Work site of Maslandapur II Piped water supply scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  | Junior Engineer | ORD/000903/2024-2025 | 935/HAB | 06/11/2024 | 16/12/2024 | ANJALI CONSTRUCTION. | 3.86 | 0 | 0 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate | SM/10533 | Augmentation |  |  |  | BILL/01349/2024-2025 | BP-2024-25-441 | 07/10/2024 | 07/10/2024 | NORTH 24 PAGRANAS DIVISION PHE. DTE. HOLDING ACCOUNT. | 86.95 | 0 | 0 | 0
Total | [13 empty] | 768.94 | 452.81 | 58.89