## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10550 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Tushkhali W/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000087/2022-2023 | 1604/BD | 07/06/2022 | 05/09/2022 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 183.73 | 164.74 | 89.67 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10550 | Retrofitting | Acceptance cum work order for Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000812/2024-2025 | 3334/BD | 28/11/2024 | 28/12/2024 | UTPAL CONSTRUCTION & CO. | 31.69 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10550 | Retrofitting | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter at Joygopalpur tail end within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000863/2024-2025 | 3378/BD | 02/12/2024 | 01/01/2025 | CHANCHAL ENTERPRISE & CO. | 31.47 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10550 | Retrofitting | Acceptance cum Work order for Construction of boundary wall with RCC column structure at Head Work site within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001307/2023-2024 | 4379/BD | 10/11/2023 | 08/02/2024 | R. B. ENTERPRISE | 21.29 | 18.48 | 86.8 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10550 | Retrofitting | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site at PH No.-1 within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001272/2024-2025 | 259/BD | 22/01/2025 | 08/03/2025 | B.S.ENTERPRISE. (BASIRHAT) | 34.32 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10550 | Retrofitting | Acceptance cum work order for Construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection at Joygopalpur tail end within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001704/2024-2025 | 951/BD | 25/03/2025 | 08/06/2025 | SABIR ALI GAZI | 8.92 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10550 | Retrofitting | Acceptance cum work order for Emergent withdrawing, relaying and laying of different dia. UPVC/DI pipe line at Tushkhali water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/001404/2024-2025 | 391/BD | 05/02/2025 | 06/04/2025 | ANKUSH CONSTRUCTION & CO. | 36.68 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10550 | Retrofitting | Acceptance cum work order for Digitalization of pipeline alignment, elevation survey and asset evaluation of 7 nos. schemes namely Jeliakhali, Bhangatushkhali, Tushkhali, Joygopalpur, Korakati, Durgamandop and Monipur under Sandeshkhali-II block in North 24 Parganas District under Hasnabad Sub-Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001599/2024-2025 | 677/BD | 04/03/2025 | 02/06/2025 | HORIZEN. | 22.46 | 6.19 | 27.57 | 80
Total | [13 empty] | 370.56 | 189.41 | 51.11