## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Construction of boundary wall within brick structure & approach road at O.H.R. site within Sultanpur Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/002645/2021-2022 | 548/BD. | 23/02/2022 | 25/03/2022 | MONDAL & CO. (BASIRHAT). | 14.69 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Acceptance cum work order for Protection works for rising main of 150mm dia. DI pipe line at pond of Muyajjem Husien Molla within Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000234/2022-2023 | 1143/HSD | 12/07/2022 | 22/07/2022 | MONDAL & CO. (BASIRHAT). | 4.69 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of different dia. UPVC pipe line at different places of Turia mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002894/2021-2022 | 603/HSD | 31/03/2022 | 15/04/2022 | ANKUSH CONSTRUCTION & CO. | 4.78 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Patkelpota abad mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002890/2021-2022 | 599/HSD | 31/03/2022 | 15/04/2022 | ANKUSH CONSTRUCTION & CO. | 4.56 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Turia Mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002878/2021-2022 | 587/HSD | 28/03/2022 | 12/04/2022 | MONDAL & CO. (BASIRHAT). | 4.57 | 0 | 0 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places of Patkelpota mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002892/2021-2022 | 601/HSD | 31/03/2022 | 15/04/2022 | TRISHA ENTERPRISE & CO. | 4.53 | 0 | 0 | 1
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Patkelpota Mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002871/2021-2022 | 579/HSD | 28/03/2022 | 12/04/2022 | ANKUSH CONSTRUCTION & CO. | 4.55 | 0 | 0 | 1
8 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of 90mm dia. UPVC pipe line at different places of Joykrishnapur mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002884/2021-2022 | 593/HSD | 29/03/2022 | 13/04/2022 | ANKUSH CONSTRUCTION & CO. | 4.86 | 0 | 0 | 1
9 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of different dia. UPVC pipe line at different places of Turia mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002886/2021-2022 | 595/HSD | 31/03/2022 | 15/04/2022 | MONDAL & CO. (BASIRHAT). | 4.81 | 0 | 0 | 1
10 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Joykrishnapur Mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002880/2021-2022 | 589/HSD | 28/03/2022 | 12/04/2022 | ANKUSH CONSTRUCTION & CO. | 4.53 | 0 | 0 | 1
11 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places of Patkelpota abad mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002882/2021-2022 | 591/HSD | 29/03/2022 | 13/04/2022 | TRISHA ENTERPRISE & CO. | 4.51 | 0 | 0 | 1
12 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) | SM/10552 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 1816/BD | 19/06/2023 | 19/06/2023 | Resource Division | 40.04 | 0 | 0 | 0
Total | [13 empty] | 101.11 | 0 | 0