## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Rajbari W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | SM/10553 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of 90 mm dia. UPVC pipe line at different places of Rajbari W/S Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000759/2022-2023 | 621/HSD | 07/04/2022 | 22/04/2022 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 1.52 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Rajbari W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | SM/10553 | Retrofitting | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep as replacement Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 250mm dia 36 mtr. long housing pipe & 150mm dia 30 mtr. long filter at Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000174/2022-2023 | 1893/BD | 05/07/2022 | 04/08/2022 | BABUSONA CONSTRUCTION. | 43.55 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Rajbari W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | SM/10553 | Retrofitting | Formal Work order for Laying of DI rising main and DI/UPVC distribution pipe line and Construction of 900 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chunchura & Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division,PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/003031/2021-2022 | 767/Bd | 16/03/2022 | 28/03/2022 | S. GHOSH & ASSOCIATES PVT. LTD. | 563.09 | 0 | 0 | 100
Total | [13 empty] | 608.16 | 0 | 0