## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Chotto Sehara W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | SM/10554 | Retrofitting | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the Sehara Radhanagar mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Chotto Sehara w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000666/2022-2023 | 2921/BD | 26/09/2022 | 26/10/2022 | TRISHA ENTERPRISE & CO. | 24 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Chotto Sehara W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | SM/10554 | Retrofitting | Acceptance cum work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chotto Sehara water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte | Assistant Engineer |  | ORD/001355/2022-2023 | 1153/BD. | 12/04/2022 | 08/12/2022 | S.S.ENTERPRISE. (BAMANGACHI) | 143.13 | 0 | 0 | 95
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Chotto Sehara W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). | SM/10554 | Retrofitting | Acceptance cum work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chotto Sehara water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000169/2022-2023 | 1153/BD | 12/04/2022 | 08/12/2022 | M/S S.S.ENTERPRISE. (SOUTH) | 146.26 | 0 | 0 | 1
Total | [13 empty] | 313.39 | 0 | 0