## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | Augmentation | Acceptance cum work order for Withdrawing & relaying of 110 mm dia. UPVC pipe line from PH no- 1 towards Adibasi Sonali Sangha of Murarisha W/S Scheme,Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001293/2022-2023 | 378/HSD | 31/03/2023 | 10/04/2023 | MD.SALIM GAZI. | 0.9 | 0.9 | 99.74 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | Augmentation | Acceptance cum work order for Withdrawing & relaying of 110 mm dia. UPVC pipe line from PH no- 1 towards Adibasi Sonali Sangha of Murarisha W/S Scheme,Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001348/2022-2023 | 378/HSD | 31/03/2023 | 10/04/2023 | MD.SALIM GAZI. | 0.9 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000241/2022-2023 | 934/BD | 22/03/2023 | 22/03/2023 | Resource Division | 27.49 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 4510/BD | 28/11/2023 | 28/11/2023 | Resource Division | 18.1 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places in connection with Augmentation of Murarisha w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001848/2023-2024 | 274/HSD | 06/03/2024 | 16/03/2024 | NEW MANGES INDUSTRIAL CORPORATION | 0.95 | 0.94 | 99.91 | 80
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI pipeline at different places in connection with Augmentation of Murarisha w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001837/2023-2024 | 268/HSD | 06/03/2024 | 16/03/2024 | NEW MANGES INDUSTRIAL CORPORATION | 0.92 | 0.91 | 98.19 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connection with Augmentation of Murarisha W/S scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001831/2023-2024 | 259/HSD | 06/03/2024 | 16/03/2024 | S.S.ENTERPRISE. (BAMANGACHI) | 0.94 | 0.94 | 100 | 37
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 250 mm dia DI pipeline at different places in connection with Augmentation of Murarisha w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000395/2024-2025 | 873/HSD | 07/08/2024 | 17/08/2024 | NEW MANGES INDUSTRIAL CORPORATION | 0.95 | 0.94 | 99.07 | 100
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III and IV(Rep.) under Murarisha W/S Scheme and Jeliakhali-Paschimkhanda (I or II) W/S Scheme in District of 24 Pgs. (N) NIET-32 of EE/EMD of 2022-23 (Sl. no.19) | Assistant Engineer | Junior Engineer | ORD/001160/2023-2024 | 4810/EMD | 09/08/2023 | 08/09/2023 | SUNRISE ENGINEERING CORPORATION | 63.65 | 0 | 0 | 75
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Murarisha w/s scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000529/2024-2025 | 2896/BD | 03/10/2024 | 31/05/2025 | M/S SUKANTA ENTERPRISE. | 51.37 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC | SM/10555 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, construction of 350 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap and providing Functional Household Tap Connection in connection with Augmentation of Murarisha water supply scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000764/2023-2024 | 2591/BD | 28/08/2023 | 31/03/2025 | S.S.ENTERPRISE. (BAMANGACHI) | 576.34 | 546.09 | 94.75 | 98
Total | [13 empty] | 742.51 | 550.72 | 74.17