## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10556 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with retrofitting of Kanmari w/s scheme (Zone-I), Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000971/2022-2023 | 99/BD | 11/01/2023 | 11/04/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 282.73 | 277.6 | 98.19 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10556 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Kanmari mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000998/2023-2024 | 1082/HSD | 31/08/2023 | 10/09/2023 | SARKAR ENTERPRISE | 0.93 | 0.92 | 99.12 | 100
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10556 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Nalkora mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/001000/2023-2024 | 1083/HSD | 31/08/2023 | 10/09/2023 | SARKAR ENTERPRISE | 0.92 | 0.92 | 99.76 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10556 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 1828/BD | 29/06/2022 | 29/06/2022 | Resource Division | 195.63 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10556 | Retrofitting | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Kanmari water supply scheme (Zone-I), Sandeshkhali-I Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001248/2023-2024 | 4180/BD | 30/10/2023 | 21/10/2026 | TRISHA ENTERPRISE & CO. | 113.9 | 72.36 | 63.53 | 70
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10556 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at PH No-1 & 2 within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001334/2023-2024 | 4406/BD | 10/11/2023 | 08/02/2024 | NIKHIL SAMADDAR | 26.72 | 10.03 | 37.55 | 70
Total | [13 empty] | 620.84 | 361.84 | 58.28