## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC | SM/10558 | Augmentation | Formal work order for for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Ashariya Narayanpur water supply scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000517/2022-2023 | 2399/BD | 17/08/2022 | 15/11/2022 | M/S DATTA ENTERPRISE. | 271.42 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC | SM/10558 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Ashariya Narayanpur w/s scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000355/2022-2023 | 2235/BD | 28/07/2022 | 27/08/2022 | M/S K.P.PAL. | 44.42 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC | SM/10558 | Augmentation | Acceptance cum work order for Repairing of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir & other allied work for Augmentation of Asharia Narayanpur water supply scheme, Hasnabad block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000058/2023-2024 | 1430/BD | 11/05/2023 | 25/06/2023 | B.S.ENTERPRISE. (BASIRHAT) | 27.62 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC | SM/10558 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 2469/BD | 24/08/2022 | 24/08/2022 | Resource Division | 15.08 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC | SM/10558 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Chhaimalpur W/S Scheme and Pump House No.I & II under Asharia-Narayanpur W/S Scheme , District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.-07) | Assistant Engineer | Junior Engineer | ORD/001672/2022-2023 | 1003/EMD | 09/03/2023 | 01/02/2025 | SWAPAN KUMAR BHANJA | 42.29 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC | SM/10558 | Augmentation | Formal work order for Repairing & renovation of existing AIRP capacity 54m3/hr for Augmentation of Ashariya Narayanpur w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001040/2024-2025 | 3713/BD | 26/12/2024 | 24/06/2025 | WIST WATER SOLUTIONS PVT. LTD. | 57.54 | 0 | 0 | 0
Total | [13 empty] | 458.37 | 0 | 0