## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC | SM/10565 | Augmentation | Work order for repairing & renovation of Pump House and allied works of Ichhapur Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/002941/2021-2022 | 540/ BON | 03/11/2021 | 24/11/2021 | ROY ENGINEERS. | 2.52 | 2.48 | 98.63 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC | SM/10565 | Augmentation | Laying of badly damaged distribution pipe line and others allied works for making Panchayet Drain at Ichhapur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001182/2023-2024 | 329/Bon | 03/05/2023 | 15/05/2023 | ROY ENGINEERS. | 0.51 | 0.25 | 49.48 | 100
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC | SM/10565 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 1363/BD | 13/05/2022 |  | Resource Division | 10.74 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC | SM/10565 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ichhapur water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000799/2023-2024 | 2698/BD | 04/09/2023 | 04/10/2023 | NADIA TUBEWELLS | 16.16 | 6.55 | 40.51 | 100
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC | SM/10565 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Ichhapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000867/2022-2023 | 3768/BD | 20/12/2022 | 20/03/2023 | BALAJI UDDYOG | 468.29 | 450.9 | 96.29 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC | SM/10565 | Augmentation | Acceptance cum work order for Laying of badly damaged UPVC Distribution Pipe Lines due to laying of Secondary Rising Main of Habra-Gaighata Project from Amkola More to Kulipara More along with Road Restoration and other allied works at ICCHAPUR Water Supply Scheme within the jurisdiction of Bongaon SubDivision, under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001576/2023-2024 | 85/BD | 08/01/2024 | 07/02/2024 | NEW MILLENNIUM ENGG'S CO-OP-SO-LTD. | 19.15 | 9.57 | 49.99 | 100
7 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC | SM/10565 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep) under Shimulpur W/S Scheme and Pump House No-I and II (Rep.) under Ichapur W/S Scheme and Kalupur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001170/2023-2024 | 4798/EMD | 09/08/2023 | 08/09/2023 | ORIENTAL ENGINEERING CO. | 91.05 | 9.88 | 10.85 | 57
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC | SM/10565 | Augmentation | Renovation and repairing of Boundary wall and Construction of Approach Road at 2nd Tube Well site under Augmentation of Ichhapur Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/002350/2023-2024 | 978/Bon | 27/12/2023 | 26/01/2024 | SAMBHU RAY CHOWDHURY. | 3.63 | 0 | 0 | 0
Total | [13 empty] | 612.05 | 479.63 | 78.36