## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Repairing & renovation of Pump House No. 1 & 2 of Khosdelpur& adj. mouzas W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002983/2021-2022 | 513/HAB | 10/12/2021 | 09/01/2022 | M/S SUKANTA ENTERPRISE. | 1.56 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000131/2022-2023 | 3798/BD | 22/12/2022 | 22/12/2022 | Resource Division | 9.95 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Kosdelpur & Adj. Mouzas Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000353/2022-2023 | 2200/BD | 26/07/2022 | 24/10/2022 | H.I.ENTERPRISE. | 333.61 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000078/2022-2023 | 3105/BD | 18/10/2022 | 18/10/2022 | Resource Division | 0.02 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Bira-Rajibpur W/S Scheme, Khasdelpur W/S Scheme and Kumarjole W/S Scheme with Pump House No-I under Sadpur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/002529/2023-2024 | 4490/EMD | 14/07/2023 | 01/01/2025 | EASTERN INDIA SALES & SERVICE | 74.22 | 0 | 0 | 90
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Construction of Service Road (30 Mtr. Length X 2 Mtr. Width) for Pump House No:1 of khosdelpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  | Junior Engineer | ORD/000475/2024-2025 | 696/HAB | 25/07/2024 | 04/08/2024 | M/S GUHA CONSTRUCTION. | 1.83 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Construction of Boundary Wall 30 m Length for Pump House No - 2 of Khosdelpur water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction Habra Sub-Division under Barasat Division P.H.E.Dte. |  | Junior Engineer | ORD/000596/2024-2025 | 912/HAB | 30/10/2024 | 09/12/2024 | M/S SUKANTA ENTERPRISE. | 4.83 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Acceptance cum work order for Construction of Service Road (15 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of Khosdelpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/001898/2023-2024 | 170/HAB | 19/02/2024 | 05/03/2024 | M/S SUKANTA ENTERPRISE. | 0.92 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Special repair and renovation of pump house and other Allied Works for Pump House No - 2 of Khosdelpur and Adj. Mouzas W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000602/2024-2025 | 915/HAB | 30/10/2024 | 19/11/2024 | M/S SUKANTA ENTERPRISE. | 2.6 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Special repair & renovation of pump house and other Allied Works for Pump House No - 1 of Khosdelpur & Adj. Mouzas W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000893/2024-2025 | 925/HAB | 05/11/2024 | 25/11/2024 | M/S SUKANTA ENTERPRISE. | 2.66 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Acceptance cum work order for Repairing of Boundary Wall for PH-1 of Khasdelpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000592/2024-2025 | 3063/BD | 25/10/2024 | 24/11/2024 | ANJALI CONSTRUCTION. | 5.08 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Khosdelpur & Adjoining Mouzas water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000914/2023-2024 | 2774/BD | 11/09/2023 | 10/11/2023 | ANJALI ENTERPRISE. | 28.99 | 0 | 0 | 80
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC | SM/10570 | Augmentation | Improvement of Iron Elimination Plant at Khosdelpur & adj. Mouzas W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001434/2023-2024 | 688/HAB | 01/11/2023 | 01/12/2023 | M/S SUKANTA ENTERPRISE. | 3.51 | 0 | 0 | 100
Total | [13 empty] | 469.79 | 0 | 0