## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate | SM/10577 | Augmentation | Repairing & renovation of Pump House No. - 1 of Sadpur W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002979/2021-2022 | 500/HAB | 02/12/2021 | 01/01/2022 | M/S SUKANTA ENTERPRISE. | 0.74 | 0.7 | 94.42 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate | SM/10577 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000135/2022-2023 | 3795/BD | 22/12/2022 | 22/12/2022 | Resource Division | 0.87 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate | SM/10577 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 1560/BD | 23/05/2023 | 23/05/2023 | Resource Division | 1.23 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate | SM/10577 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Sadpur Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000110/2023-2024 | 1669/BD | 06/06/2023 | 04/09/2023 | B.M.ENTERPRISE. | 105.99 | 43.32 | 40.87 | 80
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate | SM/10577 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Bira-Rajibpur W/S Scheme, Khasdelpur W/S Scheme and Kumarjole W/S Scheme with Pump House No-I under Sadpur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/002529/2023-2024 | 4490/EMD | 14/07/2023 | 01/01/2025 | EASTERN INDIA SALES & SERVICE | 74.22 | 3.39 | 4.57 | 90
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate | SM/10577 | Augmentation | Special repair & renovation of pump house and other allied Works for Pump House No - 1 of Sadpur W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  | Junior Engineer | ORD/001888/2023-2024 | 136/HAB | 05/02/2024 | 20/02/2024 | JOY ENTERPRISE | 0.45 | 0.44 | 98.66 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate | SM/10577 | Augmentation | Construction of Service Road 50 Mtr. Length and 2 Mtr. Width for Pump House No1 of Sadpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  | Junior Engineer | ORD/000600/2024-2025 | 783/HAB | 20/08/2024 | 30/08/2024 | JOY ENTERPRISE | 2.95 | 2.92 | 99.08 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate | SM/10577 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 for Augmentation of Sadpur water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000959/2023-2024 | 2772/BD | 11/09/2023 | 16/07/2025 | NADIA TUBEWELLS | 14.48 | 0 | 0 | 100
Total | [13 empty] | 200.93 | 50.77 | 25.27