## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | SM/10584 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Champali water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 2400/BD | 17/08/2022 | 15/11/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 129.78 | 128.23 | 98.81 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | SM/10584 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 2474/BD | 24/08/2022 | 24/08/2022 | Resource Division | 2.46 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | SM/10584 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Champali W/S Scheme and Nurpur W/S SchemeDistrict of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/001673/2022-2023 | 1004/EMD | 09/03/2023 | 08/04/2023 | PADMA ENGINEERING CO. | 53 | 26.52 | 50.04 | 60
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | SM/10584 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Champali water supply scheme, Minakhan Block under hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001247/2023-2024 | 4179/BD | 30/10/2023 | 29/10/2024 | M/S BISWAS BROTHERS. | 114.29 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | SM/10584 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Champali w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000371/2022-2023 | 2436/BD | 22/08/2022 | 21/09/2022 | AUXILIARY TUBE WELL DRILLERS. | 44.41 | 37.78 | 85.07 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | SM/10584 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation for Champali water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001907/2023-2024 | 279/HSD | 06/03/2024 | 16/03/2024 | SARKAR ENTERPRISE | 0.6 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | SM/10584 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Champali w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001370/2024-2025 | 237/HSD | 30/01/2025 | 09/02/2025 | SARKAR ENTERPRISE | 0.81 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | SM/10584 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Champali water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001612/2024-2025 | 476/HSD | 28/02/2025 | 10/03/2025 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 0.72 | 0 | 0 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC | SM/10584 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Champali water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001433/2024-2025 | 313/HSD | 04/02/2025 | 14/02/2025 | SARKAR ENTERPRISE | 0.72 | 0 | 0 | 100
Total | [13 empty] | 346.78 | 192.53 | 55.52