## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Chikonpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002935/2021-2022 | 632/BON | 31/12/2021 | 21/01/2022 | MA CONSTRUCTION. | 1.26 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Repairing & Renovation of 02No. Pump House and allied works at Chikonpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002934/2021-2022 | 586/BON | 15/12/2021 | 05/01/2022 | MA CONSTRUCTION. | 2.52 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 1368/BD | 13/05/2022 | 13/05/2022 | Resource Division | 46.36 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Renovation and repairing of Boundary wall and Construction of Approach Road at 2nd Tube Well site under Augmentation of Chikanpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/002349/2023-2024 | 977/Bon | 27/12/2023 | 26/01/2024 | M/S SAYAN ENTERPRISE. | 4.84 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chikanpara Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000864/2022-2023 | 3762/BD | 20/12/2022 | 20/03/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 481.61 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Acceptance cum work order for Renovation & repairing of Boundary wall at Head work site for Augmentation of Chikanpara water Supply scheme, Gaighata Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001480/2023-2024 | 4413/BD | 10/11/2023 | 09/01/2024 | VAI ENTERPRISE. | 10.85 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 3rd Tube Well site and Construction of Approach Road at 3rd Tube Well site and Head work site under Augmentation of Chikanpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001559/2023-2024 | 40/BD | 04/01/2024 | 27/01/2024 | M/S.RAJESH CONTRUCTION | 8.42 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep) under Chikanpara W/S Scheme and Pump House No.I, II and III under Chandpara W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001167/2023-2024 | 4795/EMD | 09/08/2023 | 01/09/2025 | DAS ENTERPRISE (M) | 78.21 | 0 | 0 | 60
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Acceptance cum work order for Special Repairing work in connection with augmentation work at total command area of Chikanpara Water Supply Scheme, to repair the damaged pipeline due to road widening and drain construction, to extend the Backwash line and also to convert the mouzas into Swajal Gram within Bongaon Sub Division, under Barasat Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000074/2025-2026 | 1904/BD | 05/06/2025 | 03/10/2025 | MA CONSTRUCTION. | 13.57 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Repairing and renovation of 150 Cum C.W.R. for Augmentation of Chikanpara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000399/2025-2026 | 816/Bon | 26/06/2025 | 10/08/2025 | MA CONSTRUCTION. | 1.8 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Construction of Latrine at Head Work site and Renovation of P/H No-1 for Chikanpara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000566/2025-2026 | 638/Bon | 21/05/2025 | 05/07/2025 | MA CONSTRUCTION. | 4.31 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chikanpara water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001168/2023-2024 | 2690/BD | 04/09/2023 | 26/01/2025 | JOY HIND TUBEWELLS. | 16.16 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC | SM/10690 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chikanpara water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001167/2023-2024 | 2686/BD | 04/09/2023 | 28/10/2024 | JOY HIND TUBEWELLS. | 16.16 | 0 | 0 | 100
Total | [13 empty] | 686.06 | 0 | 0