## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate | SM/10693 | Augmentation | Repairing & renovation of Pump House No. - 1 & 2 of Talsa W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002986/2021-2022 | 498/HAB | 02/12/2021 | 01/01/2022 | TALUKDER & CO. | 2.16 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate | SM/10693 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000128/2022-2023 | 3791/BD | 22/12/2022 | 22/12/2022 | Resource Division | 10.96 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate | SM/10693 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 2516/BD | 25/08/2022 | 25/08/2022 | Resource Division | 7.71 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate | SM/10693 | Augmentation | Special repair & renovation of pump house and other Allied Works for Pump House No - 1 of Talsa W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000894/2024-2025 | 926/HAB | 05/11/2024 | 25/11/2024 | JP CONSTRUCTION & SUPPLIERS. | 2.66 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate | SM/10693 | Augmentation | Special repair & renovation of pump house and other Allied Works for Pump House No - 2 of Talsa W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000899/2024-2025 | 931/HAB | 05/11/2024 | 25/11/2024 | M/S SUKANTA ENTERPRISE. | 2.6 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate | SM/10693 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Talsa Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 2312/BD | 03/08/2022 | 01/11/2022 | DEBAPRASAD MONDAL. | 295.79 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate | SM/10693 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Rep.) under Talsa and adj. mouzas W/S Scheme and Talsa W/S Scheme with Pump House No-I under Chandpur (Block-Hasnabad) W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001175/2023-2024 | 4803/EMD | 09/08/2023 | 08/09/2023 | M/S S.R. ENTERPRISE | 60.76 | 0 | 0 | 80
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate | SM/10693 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Talsa water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000973/2023-2024 | 2781/BD | 11/09/2023 | 10/11/2023 | M/S K.P.PAL. | 28.99 | 0 | 0 | 100
Total | [13 empty] | 411.64 | 0 | 0