## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Repairing & renovation of Pump House No. ¿ 1 & 2 of Talsa& adj. mouzas W/S scheme within the jurisdiction of Habra Sub-Division under BarasatDivision, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002985/2021-2022 | 515/HAB | 10/12/2021 | 09/01/2022 | DAS & CO. | 1.55 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000129/2022-2023 | 3792/BD | 22/12/2022 | 22/12/2022 | Resource Division | 14.47 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Talsa & Adj. Mouzas Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000414/2022-2023 | 2313/BD | 03/08/2022 | 01/11/2022 | M/S B.K.ENTERPRISE. | 230.62 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Acceptance cum work order for Construction of Service Road(10 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of Talsa & Adj Mouzas Water Supply Scheme in connection with Augmentation work undeer JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/001900/2023-2024 | 172/HAB | 19/02/2024 | 05/03/2024 | M/S LATIKA CONSTRUCTION. | 0.61 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Acceptance cum work order for Construction of Boundary Wall for Pump House No - 2 of Talsa & Adj Mouzas water Supply Scheme in connection with Augmentation work under JJM project with in the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer |  | ORD/000588/2024-2025 | 3065/BD | 25/10/2024 | 04/12/2024 | PUSPA CONSTRUCTION. | 5.62 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Special repair and renovation of pump house and other Allied Works for Pump House No - 2 of Talsa and Adj Mouzas W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000900/2024-2025 | 932/HAB | 05/11/2024 | 25/11/2024 | M/S SANKAR ENTERPRISE. | 2.58 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Special repair and renovation of pump house and other Allied Works of Pump House No - 1 under Talsa and Adj Mouzas WS scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000904/2024-2025 | 936/HAB | 06/11/2024 | 26/11/2024 | TALUKDER & CO. | 2.66 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Acceptance cum work order for Construction of Boundary Wall (90 m Length) for Pump House no 1 of Talsa & Adj Mouzas water Supply Scheme in connection with Augmentation work under JJM project with in the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer |  | ORD/000403/2024-2025 | 2583/BD | 05/09/2024 | 20/10/2024 | BRIGHT STAR CO-OP LABOUR CONTRACTOR & CONSTRUCTION SOCIETY LTD. | 14.76 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Construction of Service Road 40 Mtr. Length X 2 Mtr. Width for Pump House No 1 of Talsa and Adj Mouzas Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/000606/2024-2025 | 920/HAB | 30/10/2024 | 09/11/2024 | TALUKDER & CO. | 2.44 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Rep.) under Talsa and adj. mouzas W/S Scheme and Talsa W/S Scheme with Pump House No-I under Chandpur (Block-Hasnabad) W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001175/2023-2024 | 4803/EMD | 09/08/2023 | 08/09/2023 | M/S S.R. ENTERPRISE | 60.76 | 0 | 0 | 80
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Acceptance cum work order for Sinking of 2 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Talsa & Adj Mouzas water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000975/2023-2024 | 2779/BD | 11/09/2023 | 10/11/2023 | M/S SUKANTA ENTERPRISE. | 39.1 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC | SM/10706 | Augmentation | Improvement of Iron Elimination Plant at Talsa & Adj. Mouzas W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001423/2023-2024 | 672/HAB | 30/10/2023 | 29/11/2023 | M/S SANKAR ENTERPRISE. | 3.29 | 0 | 0 | 100
Total | [13 empty] | 378.45 | 0 | 0