## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | SM/10727 | Augmentation | Repairing & renovation of Pump House No. ? 1 & 2 of Kamarpur& adj. mouzas W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002984/2021-2022 | 512/HAB | 10/12/2021 | 09/01/2022 | M/S LATIKA CONSTRUCTION. | 1.4 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | SM/10727 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000132/2022-2023 | 3800/BD | 22/12/2022 | 22/12/2022 | Resource Division | 4.41 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | SM/10727 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 2517/BD | 25/08/2022 | 25/08/2022 | Resource Division | 6.75 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | SM/10727 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II & III (Zone-I) under Maslandapur W/S Scheme and Pump House No-I an II uuder Kamarpur-Tazpur W/S Scheme (Rep.) District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.- 26) | Assistant Engineer | Junior Engineer | ORD/001976/2022-2023 | 1320/EMD | 29/03/2023 | 28/04/2023 | M/S DILIP MITRA | 53 | 0 | 0 | 80
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | SM/10727 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Kamarpur & Adjoining Mouzas water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000912/2023-2024 | 2776/BD | 11/09/2023 | 10/11/2023 | ANJALI ENTERPRISE. | 28.99 | 0 | 0 | 65
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | SM/10727 | Augmentation | Construction of Service Road 55 Mtr. Length X 2 Mtr. Width for Pump House No1 of kamarpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/000901/2024-2025 | 934/HAB | 06/11/2024 | 16/11/2024 | M/S LATIKA CONSTRUCTION. | 3.35 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | SM/10727 | Augmentation | Special repair and renovation of pump house and other Allied Works for Pump House No - 1 of Kamarpur WS scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000608/2024-2025 | 922/HAB | 30/10/2024 | 19/11/2024 | M/S LATIKA CONSTRUCTION. | 2.66 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | SM/10727 | Augmentation | Construction of Service Road (55 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of kamarpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/000342/2024-2025 | 693/HAB | 25/07/2024 | 04/08/2024 | G.P.ENTERPRISE. | 1.22 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | SM/10727 | Augmentation | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system for Augmentation of Kamarpur & Adj. Mouzas water supply scheme within jurisdiction of Habra Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000523/2022-2023 | 2445/BD | 23/08/2022 | 21/11/2022 | CHANDA CONSTRUCTION. | 212.3 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC | SM/10727 | Augmentation | Improvement of Iron Elimination Plant at Kamarpur & adj. Mouzas W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001460/2023-2024 | 689/HAB | 01/11/2023 | 01/12/2023 | M/S LATIKA CONSTRUCTION. | 2.97 | 0 | 0 | 100
Total | [13 empty] | 317.06 | 0 | 0