## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Installation of 2 KLD UF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 | SM/10740 | Support-R&D | Acceptance cum work order for Sinking of 01 no. 100 X 50 mm. dia. 300 mtr. Deep Tube-well with PVC pipes & strainer and other allied works for installation of 02 KLD UF-RO Based Desalination Plant at Sridharkati Zone No-23, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000250/2022-2023 | 1159/HSD | 12/07/2022 | 27/07/2022 | JESMINE ENTERPRISE. | 4.61 | 4.17 | 90.54 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Installation of 2 KLD UF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 | SM/10740 | Support-R&D | Acceptance cum work order for Construction of switch room excluding sub-structure for installation of 02 KLD UF-RO Based Desalination Plant at Sridharkati Zone No-23, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000251/2022-2023 | 1160/HSD | 12/07/2022 | 02/08/2022 | JESMINE ENTERPRISE. | 1.33 | 1.18 | 88.29 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Installation of 2 KLD UF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 | SM/10740 | Support-R&D | Acceptance cum work order for Technical Assistance for Design and Demonstration of UF/RO Desalination Plant for Saline/Brackish Water Treatment for Drinking Water Supply at Sridharkati, Zone-XXIII. | Assistant Engineer | Junior Engineer | ORD/000740/2022-2023 | 3276/BD | 07/11/2022 | 07/11/2023 | DR. P.S GHOSAL | 4.72 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Installation of 2 KLD UF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 | SM/10740 | Support-R&D | Acceptance cum work order for Supply, Installation, Testing and commission of 2 KLD Desalination Ro plant; including transport, installation and GST. | Assistant Engineer |  | ORD/001500/2022-2023 | 795/HSD | 27/05/2022 | 26/06/2022 | ENVIROEXCELSIOR SOLUTIONS PVT. LTD. | 4.97 | 4.97 | 100 | 100
Total | [13 empty] | 15.63 | 10.32 | 66.01