## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Installation of 5 KLD NF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 | SM/10759 | Support-R&D | Acceptance cum work order for Construction of switch room excluding sub-structure for installation of 05 KLD NF-RO Based Desalination Plant at Sridharkati Zone No-28, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000253/2022-2023 | 1162/HSD | 12/07/2022 | 02/08/2022 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 1.33 | 1.18 | 88.29 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Installation of 5 KLD NF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 | SM/10759 | Support-R&D | Acceptance cum work order for Sinking of 01 no. 100 X 50 mm. dia. 300 mtr. Deep Tube-well with PVC pipes & strainer and other allied works for installation of 05 KLD NF-RO Based Desalination Plant at Sridharkati Zone No-28, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000252/2022-2023 | 1161/HSD | 12/07/2022 | 27/07/2022 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 4.61 | 4.13 | 89.64 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Installation of 5 KLD NF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 | SM/10759 | Support-R&D | Acceptance cum work order for Technical Assistance for Design and Demonstration of NF/RO Desalination Plant for Saline/Brackish Water Treatment for Drinking Water Supply at Sridharkati, Zone-XXVIII. | Assistant Engineer | Junior Engineer | ORD/000737/2022-2023 | 3275/BD | 07/11/2022 | 07/11/2023 | DR. P.S GHOSAL | 5.9 | 0 | 0 | 0
Total | [13 empty] | 11.84 | 5.31 | 44.82