## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gabberia to accommodate FHTC. | SM/10781 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000247/2022-2023 | 938/BD | 22/03/2023 | 22/03/2023 | Resource Division | 19.76 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gabberia to accommodate FHTC. | SM/10781 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Gabberia w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000723/2023-2024 | 2475/BD | 18/08/2023 | 17/09/2023 | M/S RAJPATH CONSTRUCTION. | 63.23 | 43.58 | 68.92 | 92
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gabberia to accommodate FHTC. | SM/10781 | Augmentation | Formal work order for "Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 300 cum capacity 20rntr. staging height R.C.C. Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection with Augmentaion of Gabberia water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000761/2023-2024 | 2526/BD | 23/08/2023 | 30/07/2025 | BALAJEE ENTERPRISES | 550.99 | 323.7 | 58.75 | 79
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gabberia to accommodate FHTC. | SM/10781 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Replacement) under Puturia W/S Scheme, Bahira W/S Scheme, Gabberia W/S Scheme and Gobindapur (Block-Bagdah) W/S Scheme, District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/001174/2023-2024 | 4802/EMD | 09/08/2023 | 08/09/2023 | M/S. SAJAHAN CHOWDHURY | 88.56 | 20.53 | 23.18 | 70
Total | [13 empty] | 722.54 | 387.81 | 53.67