## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Repairing & renovation of Pump House No. - 1 & 2 of BiraRajibpur W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002974/2021-2022 | 499/HAB | 02/12/2021 | 01/01/2022 | B.M.ENTERPRISE. | 2.15 | 2.1 | 97.44 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000130/2022-2023 | 3793/BD | 22/12/2022 | 22/12/2022 | Resource Division | 272.77 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Acceptance cum work order for the work of Hiring Diesel Luxury Car on daily basis for the Office of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte. (Period from 01-01-2023 to 30-06-2023). | Assistant Engineer | Junior Engineer | ORD/000995/2022-2023 | 3867/BD | 30/12/2022 | 29/06/2023 | DIPANKAR NASKAR. | 0.86 | 1.85 | 214.91 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Acceptance cum work order for Sinking of 2 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 of Bira Rajibpur water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000045/2023-2024 | 1410/BD | 08/05/2023 | 07/06/2023 | M/S K.P.PAL. | 39.12 | 31.66 | 80.92 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 2518/BD | 25/08/2022 | 25/08/2022 | Resource Division | 21.54 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 1554/BD | 23/05/2023 | 23/05/2023 | Resource Division | 13.55 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Bira-Rajibpur W/S Scheme, Khasdelpur W/S Scheme and Kumarjole W/S Scheme with Pump House No-I under Sadpur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/002529/2023-2024 | 4490/EMD | 14/07/2023 | 01/01/2025 | EASTERN INDIA SALES & SERVICE | 74.22 | 19.18 | 25.85 | 90
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Bira Rajibpur Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000533/2022-2023 | 2447/BD | 23/08/2022 | 29/07/2025 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 619.57 | 197.69 | 31.91 | 75
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Hiring of 1 no. of Diesel Luxury Car (Euro - IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from: 01.12.2023 to 30.11.24) | Assistant Engineer | Junior Engineer | ORD/001630/2023-2024 | 720/HAB | 23/11/2023 | 23/11/2024 | M/S LATIKA CONSTRUCTION. | 1.74 | 3.89 | 223.48 | 60
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Continuation work order Hiring of 1 no. of Diesel Luxury Car (Euro ¿ IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, for supervision of J.J.M. related work, executed within the entire jurisdiction of Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from :01.09.24 to 28.02.25) = six months |  | Junior Engineer | ORD/000400/2024-2025 | 780/HAB | 28/08/2024 | 28/02/2025 | M/S SUKANTA ENTERPRISE. | 0.86 | 1.79 | 208.06 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Continuation work order for Hiring of 1 no. of Diesel Luxury Car (Euro - IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from : 01.12.24 to 31.05.25) |  | Junior Engineer | ORD/000985/2024-2025 | 993/HAB | 29/11/2024 | 30/05/2025 | M/S LATIKA CONSTRUCTION. | 0.86 | 1.83 | 212.06 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC | SM/10782 | Augmentation | Hiring of 1 no. of Diesel Luxury Car (Euro -IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, for supervision of J.J.M. related work, executed within the entire jurisdiction of Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from :01.03.25 to 28.02.26) |  | Junior Engineer | ORD/002468/2024-2025 | 204/HAB | 27/02/2025 | 27/02/2026 | M/S SUKANTA ENTERPRISE. | 1.73 | 0 | 0 | 0
Total | [13 empty] | 1048.97 | 259.98 | 24.78