## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Sindrani (Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | Assistant Engineer | Junior Engineer | ORD/000111/2022-2023 | 1649/BD | 09/06/2022 | 07/09/2022 | MONDAL ENTERPRISE. (BARASAT) | 324.72 | 324.48 | 99.93 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Acceptance cum wok order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Sindrani (Zone-II) water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000829/2022-2023 | 3623/BD | 12/12/2022 | 27/12/2022 | NADIA TUBEWELLS | 15.07 | 12.82 | 85.1 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.03.22 to 31.08.22=184 days. | Assistant Engineer |  | ORD/003034/2021-2022 | 386/HSD | 28/02/2022 | 31/08/2022 | SUSMITA MANDAL. | 2.74 | 8.87 | 323.64 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Hiring of Vehicle for the (Diesel) for the office use as well as sites inspection of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. Period from 01.01.2023 to 31.06.2023. for 6 (six) months. |  |  | ORD/001266/2022-2023 | 676/BON | 30/12/2022 | 30/06/2023 | VAI ENTERPRISE. | 0.86 | 2.09 | 243.66 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 1669/BD | 13/06/2022 | 13/06/2022 | Resource Division | 14.85 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 3410/BD | 22/11/2022 | 22/11/2022 | Resource Division | 7.9 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Nalkora W/S Scheme and Pump House no-I and II (Zone-I)(Rep.) Chhayagharia W/S Scheme with Pump House No-I and II (Zone-II)(Rep.) under Sindrani W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/003334/2023-2024 | 4812./EMD | 09/08/2023 | 01/10/2025 | WEST BENGAL ENGINEERING CO. | 78.21 | 2.83 | 3.62 | 80
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Sindrani (Zone - II) Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001109/2023-2024 | 2922/BD | 26/09/2023 | 26/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 16.1 | 14.08 | 87.47 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Sindrani (Zone-II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001240/2023-2024 | 790/Bon | 10/10/2023 | 25/10/2023 | UPWARDS ENGINEERING PRIVATE LIMITED | 3.53 | 3.53 | 99.85 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Sindrani (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001728/2023-2024 | 522/BD | 20/02/2024 | 21/03/2024 | A.D.ENTERPRISE. | 16.87 | 16.86 | 99.99 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of DI pipe Rising Main, Distribution UPVC pipe line and Tube Well Connection under Augmentation work at Sindrani W/S Scheme (Zone - II) Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000086/2024-2025 | 1767/BD | 01/07/2024 | 28/03/2025 | M/S SUKANTA ENTERPRISE. | 18.13 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Construction of 3.60 mtr. X 3.00mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at 2nd Tube Well site at Sindrani w/s scheme (Zone-II), Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002299/2023-2024 | 209/Bon | 27/02/2024 | 12/04/2024 | SAMBHU RAY CHOWDHURY. | 4.41 | 4.4 | 99.94 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Health assessment of existing OHR of Sindrani (Zone-II) PWSS (135 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000013/2024-2025 | 686/Bon | 07/06/2024 | 22/06/2024 | RISHAN ENGINEERING CONSULTANCY | 2.91 | 2.91 | 100 | 100
14 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | New service connection at P.H.No- II ,Zone -II of Sindrani water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). |  |  | BILL/01509/2024-2025 | BP-95-24-25 | 29/08/2024 | 29/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.06 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah | SM/10786 | Augmentation | Acceptance cum work order for Hire and labour charges for staging and scaffolding, bamboo baricading and removal of rubbish for dismantling of existing OHR at Head work Site of Sindrani Zone-II Water Supply Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001700/2024-2025 | 707/BD | 06/03/2025 | 01/03/2026 | ONKAR ENTERPRISE. | 7.1 | 0 | 0 | 100
Total | [13 empty] | 519.44 | 392.88 | 75.63