## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC | SM/11523 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Zone-II) (Replacement) under Sadiknagar W/S Scheme District of 24 Pgs. (N). (SM/11523) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 25) |  |  | ORD/000596/2022-2023 | 6439/EMD | 25/11/2022 | 25/12/2022 | MAA KALI ENTERPRISE | 12.99 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC | SM/11523 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Zone-II) (Replacement) under Sadiknagar W/S Scheme District of 24 Pgs. (N). (SM/11523) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 27) |  |  | ORD/002033/2022-2023 | 6438/ EMD | 14/08/2022 | 13/09/2022 | BIDYUT KUMAR MUKHERJEE | 13.05 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC | SM/11523 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 2305/BD | 03/08/2022 | 03/08/2022 | Resource Division | 4.84 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC | SM/11523 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000166/2022-2023 | 484/BD | 17/02/2023 | 17/02/2023 | Resource Division | 4.43 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC | SM/11523 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Sadiknagar Zone-II Water Supply Scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000778/2022-2023 | 3474/BD | 01/12/2022 | 01/03/2023 | TIRUPATI ENTERPRISES | 214.95 | 0 | 0 | 80
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC | SM/11523 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Sadiknagar zone - II W/S Scheme at Basirhat - II Block under Basirhat Sub Division, PHE Dte. Capacity - 56.25 Cum/hr. | Assistant Engineer | Junior Engineer | ORD/002025/2023-2024 | 919/BD | 15/03/2024 | 14/05/2024 | MONDAL PRECISION PVT.LTD | 29.4 | 0 | 0 | 100
Total | [13 empty] | 279.66 | 0 | 0