## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | SM/11524 | Augmentation | Route Survey, Design Drawing & DPR Preparation for NALKORA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002858/2021-2022 | 202/ BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.79 | 2.61 | 93.6 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | SM/11524 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000142/2022-2023 | 3819/BD | 23/12/2022 | 23/12/2022 | Resource Division | 23.93 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | SM/11524 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Nalkora water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 3588/BD | 08/12/2022 | 07/01/2023 | SARKAR ENTERPRISE & CO. | 69.53 | 62.47 | 89.85 | 99
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | SM/11524 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Nalkora W/S Scheme including increasing the height of back wash tank at Basirhat - I Block under Basirhat Sub Division, PHE Dte. Capacity - 10.81 Cum/hr. | Assistant Engineer | Junior Engineer | ORD/002026/2023-2024 | 920/BD | 15/03/2024 | 10/11/2024 | MONDAL PRECISION PVT.LTD | 23.26 | 16.77 | 72.08 | 60
Total | [13 empty] | 119.5 | 81.85 | 68.49