## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC | SM/11525 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Zone-I) (Replacement) under Sadiknagar W/S Scheme District of 24 Pgs. (N). (SM/11525) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 24) |  | Junior Engineer | ORD/000583/2022-2023 | 6396/EMD | 24/11/2022 | 24/12/2022 | S.S.ENTERPRISES | 13.04 | 11.5 | 88.18 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC | SM/11525 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Zone-I) (Replacement) under Sadiknagar W/S Scheme District of 24 Pgs. (N). (SM/11525) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 26) |  | Junior Engineer | ORD/000584/2022-2023 | 6397/EMD | 24/11/2022 | 24/12/2022 | ESENCE ENGINEERING CONCERN | 13.08 | 11.53 | 88.2 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC | SM/11525 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Sadik Nagar Zone-I water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000825/2022-2023 | 3605/BD | 09/12/2022 | 09/03/2023 | PUSPA ENTERPRISE. | 406.99 | 395.2 | 97.1 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC | SM/11525 | Augmentation | Route Survey, Design Drawing & DPR Preparation for SADIKNAGAR-I Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002782/2021-2022 | 206/ BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.15 | 3.96 | 95.62 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC | SM/11525 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000139/2022-2023 | 3816/BD | 23/12/2022 | 23/12/2022 | Resource Division | 17.46 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC | SM/11525 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 4404/BD | 10/11/2023 | 10/11/2023 | Resource Division | 18.48 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC | SM/11525 | Augmentation | Enhancement of GST for laying of distribution pipe line and providing FHTC for Augmentation of Sadiknagar Zone -I water supply scheme under Basirhat Sub-Division, P.H.E.Dte. |  |  | BILL/01247/2024-2025 | BP-2024-25-391 | 04/10/2024 | 04/10/2024 | PUSPA ENTERPRISE. | 13.91 | 0 | 0 | 0
Total | [13 empty] | 487.1 | 422.19 | 86.67