## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | Augmentation | Repairing of Pump House No 1 at Rajandrapur Water Supply Scheme under Basirhat Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002987/2021-2022 | 1237/BHT | 16/09/2021 | 06/10/2021 | PROBAHA ENGINEER'S CO-OP-SOCIETY LTD. | 0.66 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | Augmentation | Repairing of Pump House No 1 at Rajandrapur Water Supply Scheme under Basirhat Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000369/2021-2022 | 1236 /BHTSD | 16/09/2021 | 06/10/2021 | MD AMIRUL MOLLA. | 0.64 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | Augmentation | Route Survey, Design Drawing & DPR Preparation for RAJENDRAPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002965/2021-2022 | 311/BHT | 07/03/2022 | 22/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.19 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Rajendrapur W/S Scheme District of 24 Pgs. (N). (SM/11526) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 22) |  |  | ORD/000598/2022-2023 | 6441/EMD | 25/11/2022 | 25/12/2022 | MAA TARA ENTERPRISE | 13.04 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Rajendrapur W/S Scheme (TW-II) , Barasat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000084/2023-2024 | 1648/CDD | 17/10/2023 | 16/11/2023 | DIPALI CONSTUCTION | 21.78 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000199/2022-2023 | 855/BD | 20/03/2023 | 20/03/2023 | Resource Division | 71.29 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 4416/BD | 10/11/2023 | 10/11/2023 | Resource Division | 12.32 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Rajendrapur W/S Scheme District of 24 Pgs. (N). (SM/11526) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 23) | Assistant Engineer | Junior Engineer | ORD/000597/2022-2023 | 6440/EMD | 25/11/2022 | 03/02/2023 | M.D. ENTERPRISE | 13.02 | 0 | 0 | 40
9 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Rajendrapur W/S Scheme (T/W-I) , Basirhat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000063/2023-2024 | 546/CDD | 02/06/2023 | 28/03/2024 | UNIVERSAL ENTERPRISES | 21.54 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | Augmentation | Acceptance cum work order for Restoration of roads and emergency protection work under different places of Rajendrapur Water Supply Scheme within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer |  | ORD/000294/2025-2026 | 2452/BD | 16/07/2025 | 15/08/2025 | ABDUL CHHAMAD MANDAL | 9.09 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC | SM/11526 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Rajendrapur water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001012/2022-2023 | 174/BD | 19/01/2023 | 28/03/2025 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 376.42 | 0 | 0 | 70
Total | [13 empty] | 543.99 | 0 | 0