## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC | SM/11527 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under dhobaberia W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001895/2022-2023 | 6444 / EMD | 14/08/2022 | 13/09/2022 | SINHA ELECTRICALS | 13.04 | 10.91 | 83.7 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC | SM/11527 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Zone-I) (Replacement) under Dhopaberia W/S Scheme District of 24 Pgs. (N). (SM/11527) |  |  | ORD/002106/2022-2023 | 6382 / EMD | 24/11/2022 | 24/12/2022 | ALPHA ENTERPRISE | 13.03 | 9.77 | 74.98 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC | SM/11527 | Augmentation | Supply delivery & installation of Submersible pumping machinery alongwith allied electro-Mechanical Works Voltage stabilezer and automatic chlorinator in coonection with Aug. related to FHTC at Pump House-II Z-I under Dhopaberia W/S Scheme under Dist 24 Pgs North. |  |  | ORD/002285/2022-2023 | 6445/ EMD | 14/08/2022 | 13/09/2022 | T.S.CONSTRUCTION | 9.48 | 9.48 | 100 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC | SM/11527 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Dhopaberia-Ganrakupia Water Supply Scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000846/2022-2023 | 3475/ BD | 01/12/2022 | 01/03/2023 | DIVINE | 311.55 | 303 | 97.25 | 93
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC | SM/11527 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000165/2022-2023 | 486/BD | 17/02/2023 | 17/02/2023 | Resource Division | 22.66 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC | SM/11527 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000184/2022-2023 | 597/BD | 23/02/2023 | 23/02/2023 | Resource Division | 6.69 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC | SM/11527 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 4420/BD | 10/11/2023 | 10/11/2023 | Resource Division | 4.93 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC | SM/11527 | Augmentation | Acceptance cum work order for Restoration of roads and emergency protection work under different places of Dhopaberia Water Supply Scheme within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000001/2025-2026 | 1111/BD | 08/04/2025 | 07/07/2025 | MD AMIRUL MOLLA. | 23.39 | 0 | 0 | 0
Total | [13 empty] | 404.77 | 333.16 | 82.31