## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC | SM/11528 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Srinagar W/S Scheme District of 24 Pgs. (N). (SM/11528) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 29) |  |  | ORD/000593/2022-2023 | 6436/EMD | 25/11/2022 | 25/12/2022 | AHALYA ENGINEERING WORKS | 13.04 | 7.65 | 58.69 | 0
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC | SM/11528 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Srinagar W/S Scheme District of 24 Pgs. (N). (SM/11528) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 28) |  |  | ORD/000594/2022-2023 | 6437/EMD | 25/11/2022 | 25/12/2022 | MERCURY ENGINEERING COMPANY | 13.04 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC | SM/11528 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Srinagar water supply scheme in Basirhat-II Block of North 24 Parganas district under under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000955/2022-2023 | 92/BD | 11/01/2023 | 11/04/2023 | CHANDA CONSTRUCTION. | 376.97 | 290.43 | 77.04 | 82
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC | SM/11528 | Augmentation | Route Survey, Design Drawing & DPR Preparation for SRINAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/002793/2021-2022 | 342/ BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.1 | 3.92 | 95.58 | 1
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC | SM/11528 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000167/2022-2023 | 482/BD | 17/02/2023 |  | Resource Division | 70.46 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC | SM/11528 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000187/2022-2023 | 596/BD | 23/02/2023 |  | Resource Division | 16.4 | 0 | 0 | 0
Total | [13 empty] | 494 | 302 | 61.13