## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Joypur Gopmahal water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000812/2022-2023 | 3585/BD | 08/12/2022 | 21/12/2024 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 37.54 | 18.81 | 50.1 | 100
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | Augmentation | ¿¿k¿ vghgyvuuu gb hv hv hv hv hvv vhyv vh vhcv v hvh |  |  | ORD/001988/2023-2024 |  | 15/12/2023 | 18/12/2023 | JOY ENGINEERING CO. | 0 | 0 | NAN | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300mm. x 200 mm. big dia 270 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 36 mtr. long Housing Pipe and 200 mm Dia 30 mtr. long filter for Augmentation of Joypur Gopmahal Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001024/2022-2023 | 206/BD | 24/01/2023 | 23/02/2023 | MONDAL & CO. (BASIRHAT). | 39.55 | 38.28 | 96.77 | 100
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I and II under Joypur Gopmahal ground water based water supply scheme under Block_ Bashirhat Dist. - 24Pgs(N) under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001989/2023-2024 | 6969/EMD | 15/12/2023 | 15/03/2024 | M/S DILIP MITRA | 20.49 | 19.99 | 97.54 | 57
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000168/2022-2023 | 483/BD | 17/02/2023 | 17/02/2023 | Resource Division | 0.55 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | Augmentation | Acceptance cum work order for Special repair and renovation of existing structures like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Itinda Panitor, Joypur Gopmahal, Kachua Swarupnagar, Mathurapur, Mirzanagar, Nalkora, Paikardanga, Pifa and Gobindapur Water Supply Scheme of different block under Basirhat Sub-Division within Barasat Division, P.H.E Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 2474/BD | 17/07/2025 | 14/12/2025 | SAHA CONSTRUCTION & CO | 91.3 | 0 | 0 | 0
Total | [13 empty] | 189.44 | 77.08 | 40.69