## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | Augmentation | ¿¿k¿ vghgyvuuu gb hv hv hv hv hvv vhyv vh vhcv v hvh |  |  | ORD/001988/2023-2024 | null | 15/12/2023 | 18/12/2023 | JOY ENGINEERING CO. | 0 | 0 | NAN | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Joypur Gopmahal water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000812/2022-2023 | 3585/BD | 08/12/2022 | 07/01/2023 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 37.54 | 18.81 | 50.1 | 58
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300mm. x 200 mm. big dia 270 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 36 mtr. long Housing Pipe and 200 mm Dia 30 mtr. long filter for Augmentation of Joypur Gopmahal Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001024/2022-2023 | 206/BD | 24/01/2023 | 23/02/2023 | MONDAL & CO. (BASIRHAT). | 39.55 | 38.28 | 96.77 | 100
4 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I and II under Joypur Gopmahal ground water based water supply scheme under Block_ Bashirhat Dist. - 24Pgs(N) under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001989/2023-2024 | 6969/EMD | 15/12/2023 | 14/03/2024 | M/S DILIP MITRA | 20.49 | 0 | 0 | 57
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC | SM/11529 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000168/2022-2023 | 483/BD | 17/02/2023 |  | Resource Division | 0.55 | 0 | 0 | 0
Total | [13 empty] | 98.13 | 57.09 | 58.17