## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC | SM/11530 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Mathurapur W/S Scheme District of 24 Pgs. (N). (SM/11530) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 13) |  |  | ORD/000599/2022-2023 | 6442/EMD | 25/11/2022 | 25/12/2022 | TRIO CONCERN | 13.02 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC | SM/11530 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Mathurapur W/S Scheme District of 24 Pgs. (N). (SM/11530) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 14) |  |  | ORD/000563/2022-2023 | 6388/EMD | 24/11/2022 | 24/12/2022 | POLYCON ENGINEERS | 13.04 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC | SM/11530 | Augmentation | Supply & delivery of Change over Switch at different pump houses (Atapur P.H. No. II, Mathurapur P.H. No. I & II, Pipha P.H. No. I, Rejendrapur P.H. No. I, Fakirtakia P.H. No. I and Paltadanga P.H. No. I) related to JJM Work, Dist. 24 Pgs. (N). |  |  | ORD/000110/2023-2024 | 1508/EMSD-I | 21/06/2023 | 01/07/2023 | BISALAXMI ENTERPRISE | 1.33 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC | SM/11530 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Mathurapur W/S Scheme (TW-I), Barasat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000152/2023-2024 | 1650/CDD | 17/10/2023 | 16/11/2023 | DEV AND COMPANY | 22.01 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC | SM/11530 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000159/2022-2023 | 496/BD | 17/02/2023 | 17/02/2023 | Resource Division | 29.48 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC | SM/11530 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 4419/BD | 10/11/2023 | 10/11/2023 | Resource Division | 9.24 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC | SM/11530 | Augmentation | Special repairing of rising mains pipe lines at Mathurapur water supply scheme under Basirhat Sub-Division under Barasat Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000259/2024-2025 | 1030/BHTSD | 28/06/2024 | 05/07/2024 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC | SM/11530 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Mathurapur Water Supply Scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000783/2022-2023 | 3490/BD | 02/12/2022 | 02/03/2023 | M/S DATTA ENTERPRISE. | 325.16 | 0 | 0 | 76
Total | [13 empty] | 414.18 | 0 | 0