## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC | SM/11531 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000141/2022-2023 | 3818/BD | 23/12/2022 | 23/12/2022 | Resource Division | 27.79 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC | SM/11531 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Raharhati W/S Scheme District of 24 Pgs. (N). (SM/11531) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 21) |  |  | ORD/000582/2022-2023 | 6395/EMD | 24/11/2022 | 24/12/2022 | WIZARDTECH SOLUTION | 13.02 | 11.37 | 87.34 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC | SM/11531 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Raharhati W/S Scheme District of 24 Pgs. (N). (SM/11531) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 20) |  |  | ORD/000581/2022-2023 | 6394/EMD | 24/11/2022 | 24/12/2022 | S.S. ENTERPRISE | 13.02 | 11.42 | 87.73 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC | SM/11531 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 300 mtr deep Tubewell by D.R. Rig method, with 300 mm dia 36.0 mtr. long PVC having 200mm dia 30 mtr. long filter for Augmentation of Raharati Water Supply Scheme in Basirhat-II Block of Basirhat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/001924/2023-2024 | 769/BD | 11/03/2024 | 10/04/2024 | SHEKH ENTERPRISE | 21.75 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC | SM/11531 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Raharhati water supply scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000738/2022-2023 | 3306/BD | 10/11/2022 | 08/02/2023 | M/S PRADIP KUMAR PAL | 139.59 | 139.49 | 99.93 | 99
Total | [13 empty] | 215.17 | 162.28 | 75.42