## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Route Survey, Design Drawing & DPR Preparation for GOBINDAPUR DHOKRA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002781/2021-2022 | 205/ BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.86 | 3.77 | 97.55 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Gobindapur-Dhokra W/S Scheme District of 24 Pgs. (N). (SM/11532) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 07) |  |  | ORD/000600/2022-2023 | 6443/EMD | 25/11/2022 | 25/12/2022 | CINZANO | 13.04 | 7.39 | 56.7 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Gobindapur dhokra W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001900/2022-2023 | 6383 / EMD | 14/08/2022 | 13/09/2022 | INDRANI ENTERPRISE | 13.02 | 9.85 | 75.65 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 1062/BD | 04/04/2023 | 04/04/2023 | Resource Division | 53.92 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Chak Farasatpur Mouza between Node Number 123 & 124 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of Piling Work = 33) | Assistant Engineer |  | ORD/000087/2024-2025 | 938/BHTSD | 24/05/2024 | 31/05/2024 | PRASANTA KUMAR PAUL. | 0.98 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Ramnarayanpur Mouza between Node Number 27 & 29 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of Piling Work = 30) | Assistant Engineer |  | ORD/000089/2024-2025 | 939/BHTSD | 24/05/2024 | 31/05/2024 | J.D.ENTERPRISE. (BASIRHAT) | 0.91 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gobindapur Dhokra water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001009/2022-2023 | 172/BD | 19/01/2023 | 19/04/2023 | M/S MALLICK ENTERPRISE | 373.91 | 373.72 | 99.95 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 293 to 295, 101 to 422) of Gobindapur Dhokra pwss under Basirhat Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000448/2024-2025 | 1161/BHTSD | 30/07/2024 | 14/08/2024 | MALLICK ENTERPRISE | 0.95 | 0 | 0 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 230 to 230A, 293 to 294, 232 to 233) of Gobindapur Dhokra pwss under Basirhat Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000449/2024-2025 | 1162/BHTSD | 30/07/2024 | 14/08/2024 | MALLICK ENTERPRISE | 0.9 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 266A to 266B, 276 to 277, 290 to 293) of Gobindapur Dhokra pwss under Basirhat Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000450/2024-2025 | 1163/BHTSD | 30/07/2024 | 14/08/2024 | MALLICK ENTERPRISE | 0.78 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Restoration of sub-base of bituminous road from Node 40 to 2 to 65 to 62 to 68 in Gobindapur Dhokra W/S Scheme Under Basirhat Sub-Division P.H.E. Dte.Under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000063/2024-2025 | 918/BHTSD | 24/05/2024 | 31/05/2024 | M/S MAA TARA ENTERPRISE | 0.64 | 0.62 | 96.68 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Ramnarayanpur Mouza between Node Number 27 & 28 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of Piling Work = 24) | Assistant Engineer | Junior Engineer | ORD/000091/2024-2025 | 940/BHTSD | 24/05/2024 | 31/05/2024 | SELIM GAZI. | 0.73 | 0.73 | 99.94 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Restoration of sub-base of bituminous road from Node 68 to 63 to 50 to 48 to 34 to 32 to 21 in Gobindapur Dhokra W/S Scheme Under Basirhat Sub-Division P.H.E. Dte.Under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000062/2024-2025 | 917/BHTSD | 24/05/2024 | 31/05/2024 | M/S MAA TARA ENTERPRISE | 0.92 | 0.9 | 98.32 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Repair of OHR & Pump House and emergency repairing of pipeline in Gobindapur Dhokra W/S Scheme Under Basirhat Sub-Division P.H.E. Dte.Under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000447/2024-2025 | 1170/BHTSD | 30/07/2024 | 14/08/2024 | SELIM GAZI. | 0.95 | 0.94 | 98.96 | 100
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 82 to 84, 84 to 86, 725 to 726, 545 to 549, 546 to 552 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000443/2024-2025 | 1167/BHTSD | 30/07/2024 | 14/08/2024 | M/S MAA TARA ENTERPRISE | 0.99 | 0.99 | 100 | 100
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 711 to 718, 542 to 546, 552 to 554 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000441/2024-2025 | 1165/BHTSD | 30/07/2024 | 14/08/2024 | SWADESH MONDAL. | 0.95 | 0.95 | 100.02 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 549 to 551, 511 to 538, 575 to 579 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000442/2024-2025 | 1166/BHTSD | 30/07/2024 | 14/08/2024 | PRASANTA KUMAR PAUL. | 0.97 | 0.97 | 100 | 100
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 129 to 130, 291 to 296, 509 to 507, 503 to 507, 571 to 573, 573 tp 575, 554 to 555, 65 to 66, 456 to 457 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000455/2024-2025 | 1164/BHTSD | 30/07/2024 | 14/08/2024 | MALLICK ENTERPRISE | 0.95 | 0 | 0 | 100
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 72 to 80 to 81, 73 to 74, 80 to 82, 538 to 539, 736 to 737 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000444/2024-2025 | 1168/BHTSD | 30/07/2024 | 14/08/2024 | MD AMIRUL MOLLA. | 0.98 | 0.98 | 100 | 100
20 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC | SM/11532 | Augmentation | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Chak Farasatpur Mouza between Node Number 124 & 126 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of piling work = 32 m) | Assistant Engineer | Junior Engineer | ORD/000084/2024-2025 | 937/BHTSD | 24/05/2024 | 31/05/2024 | TAJMAHAL ENTERPRISE | 0.98 | 0 | 0 | 100
Total | [13 empty] | 471.33 | 401.8 | 85.25